## Amendment 01 (2)
Selection of SPD for setting up of 15 MW Grid Connected Floating Solar PV Power Project at Nangal Pond, Near Vilage Neilla, District Bilaspur, Himachal Pradesh
SECI/C&P/SPD/RfS/15MW/BBMB/072020
Amendment 02 to the RfS
Sl. No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Category (Finance/Technical/Contractual) | Amendment 01
1 | Invitation for Bids (IFB) | 2 of 10 | New CLAUSE AT THE START OF IFB | NEW CLAUSE | Contractual | MINISTRY OF NEW & RENEWABLE ENERGY VIDE OM NO 283/3/2018-GRID SOLAR DATED 09.03.2021 HAS NOTIFIED THE IMPOSITION OF BASIC CUSTOMS DUTY (BCD) ON SOLAR PV MODULES & CELLS WITH EFFECT FROM 01.04.2022. POST THIS DATE SOLAR MODULES WILL ATTRACT BCD @ 40% & SOLAR CELLS WILL ATTRACT BCD @ 25%. BIDDER’S ARE REQUIRED TO TAKE NOTE OF THIS TRAJECTORY & BID ACCORDINGLY, AS THE IMPOSITION OF BCD AS PER THIS MENTIONED TRAJECTORY WILL NOT BE CONSIDERED UNDER CHANGE IN LAW.
2 | BID INFORMATION SHEET | 3 | (A) | 2. Single Point Connectivity at the voltage level of 66 kV of the Sub-station of FSPV Power Plant where it interconnects to the LILO connection of BBMB | Technical | 2. Single Point Connectivity at the voltage level of 33 kV of the Sub-station of FSPV Power Plant where it interconnects to the 33kV/66kV BBMB substation thorugh a BBMB line.
3 | Bid Information Sheet | 4 | S.No. H |  | Contractual
4 | Bid Information Sheet | 5 | S.No. O |  | Contractual
5 | Bid Information Sheet | 5 | S. No. P |  | Contractual
6 | DEFINITIONS OF TERMS | 8 | 1.3 A | New Definition 1.3 A |  | BBMB shall mean "BHAKRA BEAS MANAGEMENT BOARD CHANDIGARH" as a Buying Utility/Buying Entity
7 | DEFINITIONS OF TERMS | 11 | 1.25 | “INTER-CONNECTION POINT/ DELIVERY/ METERING POINT” “shall mean the single point at the voltage level of 66 kV of the Sub-station of FSPV Power Plant gantry where it interconnects to the LILO connection.” For interconnection with LILO connection and metering, the SPD shall abide by the relevant CERC Regulations, Grid Code and Central Electricity Authority (Installation and Operation of Meters) Regulations, 2006 as amended and revised from time to time or orders passed thereunder by the appropriate commission or CEA. | Technical | “INTER-CONNECTION POINT/ DELIVERY/ METERING POINT” “shall mean the single point at the voltage level of 33 kV of the Sub-station of FSPV Power Plant gantry where it interconnects to the dedicated transmission line/BBMB line connecting to the 33kV/66kV BBMB substation.” For interconnection with 33kV/66kV BBMB substation through BBMB line and metering, the SPD shall abide by the relevant CERC Regulations, Grid Code and Central Electricity Authority (Installation and Operation of Meters) Regulations, 2006 as amended and revised from time to time or orders passed there under by the appropriate commission or CEA.
8 | DEFINITIONS OF TERMS | 11 | 1.3 | LILO Connection” Shall mean dedicated 66 KV transmission line/network to be set up by BBMB for interconnecting the 66KV FSPV substation to 66 KV HPSEB line. | Technical | Deleted.
9 | DEFINITIONS OF TERMS | 12 | 1.38 | “POWER PROJECT” or “FLOATING SOLAR PROJECT” or “PROJECT” shall mean the floating solar power generation facility/ies comprising single unit at single location, having single point of injection into LILO connection of BBMB at Interconnection/ Delivery/ Metering Point. | Technical | “POWER PROJECT” or “FLOATING SOLAR PROJECT” or “PROJECT” shall mean the floating solar power generation facility/ies comprising single unit at single location, having single point of injection into 33kV/66kV BBMB substation at Interconnection/ Delivery/ Metering Point through BBMB line.
10 | DEFINITIONS OF TERMS | 12 | 1.4 | “PROJECT COMMISSIONING”: The Project will be considered as commissioned if all equipment as per rated project capacity has been installed and energy has flown into existing 66KV HPSEB line through LILO connection, in line with theCommissioning procedures defined in the RfS/ PPA; | Contractual | “PROJECT COMMISSIONING”: The Project will be considered as commissioned if all equipment as per rated project capacity has been installed and energy has flown into 33KV/66kV BBMB substation, in line with the Commissioning procedures defined in the RfS/ PPA;
11 | DEFINITIONS OF TERMS | 13 | 1.46 | “SOLAR PV PROJECT” shall mean the Solar Photo Voltaic Power Project that uses sunlight for direct conversion into electricity through Photo Voltaic Technology; “SUBSTATION” shall mean FSPV substation which shall be constructed and maintained by the SPD to get connected to the Delivery Point. The voltage level shall be 66kV. Further, the metering of the power shall be done at the Delivery Point. | Contractual | “SOLAR PV PROJECT” shall mean the Solar Photo Voltaic Power Project that uses sunlight for direct conversion into electricity through Photo Voltaic Technology; “SUBSTATION” shall mean FSPV substation which shall be constructed and maintained by the SPD to get connected to the Delivery Point. The voltage level shall be 33kV. Further, the metering of the power shall be done at the Delivery Point.
12 | Section I | 13 | 1.48 | “Unit/ Part Commissioning”: Subject to the compliance of conditions / procedure as detailed under Schedule-2 of this Agreement, Unit / Part Commissioning shall mean the Floating Solar PV Capacity (AC MW) to be commissioned as per provisions of this Agreement and RfS document. Part Commissioning shall be applicable for Projects having capacity not less than 08 MW | Technical | Part Commissioning not allowed.
13 | Invitation for Bids (IFB) | 16 | 6 | BBMB shall enter into PPA with successful SPDs for a period of 25 years from the date as per the provisions of PPA. The maximum levelised tariff payable to the Project Developer is fixed at INR 3.41/ kWh for 25 years. This shall be inclusive of all statutory taxes, duties, levies, cess applicable as on the last date of bid submission. | Contractual | BBMB shall enter into PPA with successful SPDs for a period of 25 years from the date as per the provisions of PPA. The maximum levelised tariff payable to the Project Developer is fixed at INR 3.34/ kWh for 25 years. This shall be inclusive of all statutory taxes, duties, levies, cess applicable as on the last date of bid submission.
14 | INSTRUCTIONS TO BIDDERS | 24 | 7.1 | The plant should be designed for interconnection with the LILO connection of BBMB at the voltage level of 66 kV. The Bidder should indicate substation location, voltage level in line with clause 20 below. | Technical | The plant should be designed for interconnection with the 33kv/66kv BBMB subtation at the voltage level of 33 kV. The Bidder should indicate substation location, voltage level in line with clause 20 below.
15 | INSTRUCTIONS TO BIDDERS | 24 | 7.2 (h) | Obtaining Long Term Access (LTA) upto the delivery point, for evacuation of the Contracted Capacity and maintaining it throughout the term of the Agreement. Beyond delivery point, it shall be responsibility of BBMB to avail necessary clearances from HPSEB or concerned authorities such as obtaining LTA etc., for evacuation of the Contracted Capacity from delivery point to HPSEB line and maintaining it throughout the term of PPA. | Technical | Obtaining Long Term Access (LTA) upto the delivery point, for evacuation of the Contracted Capacity and maintaining it throughout the term of the Agreement. Beyond delivery point, it shall be responsibility of BBMB to avail necessary clearances from concerned authorities such as obtaining LTA etc., for evacuation of the Contracted Capacity from delivery point to 33KV/66KV BBMB substation and maintaining it throughout the term of PPA
16 | Section III (ITB) | 26 | 8.1 | CRITERIA FOR GENERATION The Bidders will declare the annual CUF of the Project at the time of submission of response to RfS, and the SPDs will be allowed to revise the same once within first year of COD. Thereafter, the CUF for the Project shall remain unchanged for the entire term of the PPA. The declared annual CUF shall in no case be less than 21 %. It shall be the responsibility of the SPD, entirely at its cost and expense to install such number of Floating Solar panels and associated equipment (including arrangement of extra Reservoir/land for such installation) as may be necessary to achieve the required CUF, and for this purpose SPD shall make its own study and investigation of the GHI and other factors prevalent in the area which have implication on the quantum of generation. SPD shall maintain generation so as to achieve annual CUF within + 10% and -15% of the declared value till the end of 10 years from COD, subject to the annual CUF remaining minimum of 18%, and within +10% and -20% of the declared value of the annual CUF thereafter till the end of the PPA duration of 25 years. The lower limit will, however, be relaxable by BBMB to the extent of non-availability of grid for evacuation which is beyond the control of the SPD. The annual CUF will be calculated every year from 1st April of the year to 31st March next year. | Technical | CRITERIA FOR GENERATION The Bidders will declare the annual CUF of the Project at the time of submission of response to RfS, and the SPDs will be allowed to revise the same once within first year of COD. Thereafter, the CUF for the Project shall remain unchanged for the entire term of the PPA. The declared annual CUF shall in no case be less than 21.41%. It shall be the responsibility of the SPD, entirely at its cost and expense to install such number of Floating Solar panels and associated equipment (including arrangement of extra Reservoir/land for such installation) as may be necessary to achieve the required CUF, and for this purpose SPD shall make its own study and investigation of the GHI and other factors prevalent in the area which have implication on the quantum of generation. SPD shall maintain generation so as to achieve annual CUF within + 10% and -15% of the declared value till the end of 10 years from COD, subject to the annual CUF remaining minimum of 18%, and within +10% and -20% of the declared value of the annual CUF thereafter till the end of the PPA duration of 25 years. The lower limit will, however, be relaxable by BBMB to the extent of non-availability of grid for evacuation which is beyond the control of the SPD. The annual CUF will be calculated every year from 1st April of the year to 31st March next year.
17 | Section III | 27 | 8.4 a. | Generation compensation for Off-take constraints Generation Compensation in offtake constraint due to Transmission Infrastructure not complete/ ready (Transmission constraint): After the Scheduled Commissioning Date, subject to the submission of documentary evidences from the Competent Authority, if the plant is ready in all respects upto the delivery point to connect to the LILO connection but the necessary power evacuation/ transmission infrastructure is not ready, for reasons not attributable to the SPD, leading to offtake constraint, the generation compensation shall be restricted to the following and there shall be no other claim, directly or indirectly against BBMB: However, it is clarified that if the Project is ready for commissioning prior to the Scheduled Commissioning Date, but the offtake is constrained because of inadequate/incomplete power evacuation infrastructure up to the delivery point for the reasons attributable to SPD, no compensation shall be permissible. However, it is also clarified that if the plant is ready in all respects upto the delivery point to connect to the LILO connection and it is also ready to evacuate the power to HPSEB line but the necessary power evacuation/ transmission infrastructure is not ready at the end of all or any of the Partner/Beneficiary States of BBMB leading to offtake constraint (full or part), then BBMB shall compensate SPD as per this clause, assuming the off take constraint is due to BBMB only. | Contractual | Generation compensation for Off-take constraints Generation Compensation in offtake constraint due to Transmission Infrastructure not complete/ ready (Transmission constraint): After the Scheduled Commissioning Date, subject to the submission of documentary evidences from the Competent Authority, if the plant is ready in all respects upto the delivery point to connect to the to the 33kV/66kV BBMB substation but the necessary power evacuation/ transmission infrastructure is not ready, for reasons not attributable to the SPD, leading to offtake constraint, the generation compensation shall be restricted to the following and there shall be no other claim, directly or indirectly against BBMB: However, it is clarified that if the Project is ready for commissioning prior to the Scheduled Commissioning Date, but the offtake is constrained because of inadequate/incomplete power evacuation infrastructure up to the delivery point for the reasons attributable to SPD, no compensation shall be permissible. However, it is also clarified that if the plant is ready in all respects upto the delivery point to connect to the 33kV/66kV BBMB substation and it is also ready to evacuate the power to the 33kV/66kV BBMB substationbut the necessary power evacuation/ transmission infrastructure is not ready at the end of all or any of the Partner/Beneficiary States of BBMB leading to offtake constraint (full or part), then BBMB shall compensate SPD as per this clause, assuming the off take constraint is due to BBMB only. Generation compensation for Off-take constraints Generation Compensation in offtake constraint due to Transmission Infrastructure not complete/ ready (Transmission constraint): After the Scheduled Commissioning Date, subject to the submission of documentary evidences from the Competent Authority, if the plant is ready in all respects upto the delivery point to connect to the 33kV/66kV BBMB substation through a dedicated transmission Line but the necessary power evacuation/ transmission infrastructure is not ready, for reasons not attributable to the SPD, leading to offtake constraint, the generation compensation shall be restricted to the following and there shall be no other claim, directly or indirectly against BBMB
18 | Section III | 31 | 9.1 (e) | A letter from the BBMB confirming technical feasibility of connectivity of plant to the LILO point of BBMB. | Contractual | A letter from the BBMB confirming technical feasibility of connectivity of plant to the 33kV/66kV BBMB substation thorugh BBMB line from gantry of the FSPV s/s to 33kv/66kv s/s
19 | ITB SECTION -III | 31 | 10.1 | Earnest Money Deposit (EMD) of INR 1,35,00,000 Lakhs (Indian Rupee One Crore Thirty Five Lakhs Only) in the form of Bank Guarantee according to Format 7.3A and valid for 09 months from the last date of bid submission, shall be submitted by the Bidder along with their bid, failing which the bid shall be summarily rejected. The Bank Guarantees towards EMD have to be issued in the name of the Bidding Company/ Lead Member of Bidding Consortium. In the event of encashment of EMD, the encashed amount shall include all applicable taxes. | Contractual | The applicability/Non-applicability of Earnest Money Deposit (EMD) is specified under BID INFORMATION SHEET (BIS). In case of not-applicable than bidder shall submit given Format 7.3C. In case of applicable than Earnest Money Deposit (EMD) of mentioned amount in the form of Bank Guarantee according to Format 7.3A and valid for 09 months from the last date of bid submission, shall be submitted by the Bidder along with their bid, failing which the bid shall be summarily rejected. The Bank Guarantees towards EMD have to be issued in the name of the Bidding Company/ Lead Member of Bidding Consortium. In the event of encashment of EMD, the encashed amount shall include all applicable taxes.............
20 |  | 33 | 11.3 | The SPD shall furnish the PBG from any of the Banks listed at Schedule-2 of draft PPA to BBMB. PBG issued by foreign branch of a bank from bank list given in Schedule-2 of draft PPA is to be endorsed by the Indian branch of the same bank or State Bank of India (SBI). | Contractual | The SPD shall furnish the PBG from any of the Scheduled Commercial Banks as listed on the website of Reserve Bank of India (RBI) and amended as on the date of issuance of bank guarantee. Bank Guarantee issued by foreign branch of a Scheduled Commercial Bank is to be endorsed by the Indian branch of the same bank or State Bank of India (SBI). In case of the Project being implemented through an SPV incorporated by the successful bidder, the PBG shall be furnished in the name of the SPV, except for the case as indicated in Section-IV, Clause C.1 (b) of the RfS.
21 |  | 33 |  | The format of the Bank Guarantees prescribed in the Formats 7.3 A (EMD) and 7.3 B (PBG) shall be strictly adhered to and any deviation from the above Formats shall result in rejection of the EMD/ PBG and consequently, the bid. In case of deviations in the formats of the Bank Guarantees, the corresponding PPA shall not be signed. | Contractual | The format of the Bank Guarantees prescribed in the Formats 7.3 B and 7.3 C shall be strictly adhered to and any deviation from the above Formats shall result in rejection of the PBG and consequently, the bid. In case of deviations in the formats of the Bank Guarantees, the corresponding PPA shall not be signed.
22 | SECTION - III (ITB) | 36 | 18.3 | In case of Project being execute through SPVs: The successful Bidder, if being a single company, shall ensure that its shareholding in the SPV/ Project Company executing the PPA, shall not fall below 51%at any time prior to 03 (Three) years from the COD, except with the prior approval of SECI. In the event the successful bidder is a consortium, then the combined shareholding of the consortium members in the SPV/ Project Company executing the PPA, shall not fall below 51% at any time prior to 03 (Three) years from COD, except with the prior approval of SECI. However, in case the Project is being set up by a listed Company, this condition will not be applicable. | Contractual | In case of Project being execute through SPVs: The Selected Bidder executing the Project, if being a single company, shall ensure that its shareholding in the SPV/ Project Company executing the PPA, shall not fall below 51% at any time prior to 01 (one) year after the COD, except with the prior approval of SECI. In the event the selected Bidder is a consortium, then the combined shareholding of the consortium members in the SPV/ Project Company executing the PPA, shall not fall below 51% at any time prior to 01 (one) year after COD, except with the prior approval of SECI. However, in case the Project is being set up by a listed Company, this condition will not be applicable.
23 | SECTION - III (ITB) | 36 | 18.4 | In case of the successful Bidder itself executing the PPA, it shall ensure that its promotors shall not cede control (Control shall mean the ownership, directly or indirectly, of more than 50% of the voting shares of such Company or right to appoint majority Directors), till 03 (Three) years from the COD, except with the prior approval of SECI. However, in case the Project is being set up by a listed Company, this condition will not be applicable. | Contractual | In case of the successful Bidder itself executing the PPA, it shall ensure that its promotors shall not cede control (Control shall mean the ownership, directly or indirectly, of more than 50% of the voting shares of such Company or right to appoint majority Directors), till 01 (One) years from the COD, except with the prior approval of SECI. However, in case the Project is being set up by a listed Company, this condition will not be applicable.
24 | SECTION - III (ITB) | 36 | 18.5 | In case of companies having multiple promoters (but none of the shareholders having more than 50% of voting rights and paid up share capital), it shall be considered as a company under joint control. In such cases, the shareholding pattern in the company as submitted at the time of bidding, shall be maintained for a period of 03 (Three) years after COD. | Contractual | In case of companies having multiple promoters (but none of the shareholders having more than 50% of voting rights and paid up share capital), it shall be considered as a company under joint control. In such cases, the shareholding pattern in the company as submitted at the time of bidding, shall be maintained for a period of 01 (One) years after COD.
25 | SECTION - III (ITB) | 36 | 18.6 | Any change in the shareholding after the expiry of 03 years from COD can be undertaken under intimation to SECI. Transfer of controlling shareholding of the company developing the project within the same group of companies will however be allowed after COD with the permission of SECI, subject to the condition that, the management control remains within the same group of companies. | Contractual | Any change in the shareholding after the expiry of 01 years from COD can be undertaken under intimation to SECI. Transfer of controlling shareholding of the company developing the project within the same group of companies will however be allowed after COD with the permission of SECI, subject to the condition that, the management control remains within the same group of companies.
26 | SECTION - III (ITB) | 38 | 16.a | Part commissioning of the Project shall be accepted by SECI & BBMB in accordance with “Schedule 2: Commissioning Procedure” of the PPA. Part commissioning of the Project shall be accepted by SECI subject to the condition that the minimum capacity for acceptance of first and subsequent part(s) commissioning shall be 08 MW, without prejudice to the imposition of liquidated damages, in terms of the PPA on the part which is not commissioned. For example, a project of 15 MW may be commissioned in 2 parts: First being a part capacity of 08 MW and the remaining part capacity being 07 MW. However, the SCD will not get altered due to part commissioning. Irrespective of dates of part commissioning or full commissioning, the PPA will remain in force for a period of 25 (twenty five) years from the SCD. | Contractual | Part Commissioning not allowed
27 | Section III, ITB | 39 | 16.c | The SPD shall be permitted for part / full commissioning of the Project even prior to the SCD. In such case the BBMB shall purchase the generation at PPA Tariff. | Technical | The SPD shall be permitted for full commissioning of the Project even prior to the SCD. In such case the BBMB shall purchase the generation at PPA Tariff.
28 |  | 39 |  | The SPD shall be permitted for part / full commissioning of the Project even prior to the SCD. In such case the BBMB shall purchase the generation at PPA Tariff. | Contractual | The SPD shall be permitted for full commissioning of the Project even prior to the SCD. In such case the BBMB may purchase the generation at PPA Tariff. Such intimation for early commissioning shall be provided to BBMB at least 15 days prior to the proposed early commissioning date. In case there is no response provided by BBMB within 7 days from the receipt of such intimation, such early commissioned capacity shall be deemed to have been refused by BBMB.
29 | Qualification Requirement SECTION - | 55 | C2 | A minimum annual turnover of INR 9.45 Crores during the previous financial year, i.e. FY 2018-19. It is hereby clarified that “Other Income” as indicated in the annual accounts of the Bidder shall not be considered for arriving at the annual turnover. Internal resource generation capability, in the form of Profit Before Depreciation Interest and Taxes (PBDIT) for a minimum amount of INR 1.89 Crore, as on the last date of previous financial year, i.e. FY 2018-19. In-principle sanction letter from the lending institutions/ banks of the Bidder, committing a Line of Credit for a minimum amount of INR 2.36 Crore, towards meeting the working capital requirement of the project quoted under this RfS. Such letter can also be obtained by the Affiliate(s) of the Bidder.................. | Financial | A minimum annual turnover of INR 9.40 Crores during the previous financial year, i.e. FY 2019-20 or FY2020-21. It is hereby clarified that “Other Income” as indicated in the annual accounts of the Bidder shall not be considered for arriving at the annual turnover. Internal resource generation capability, in the form of Profit Before Depreciation Interest and Taxes (PBDIT) for a minimum amount of INR 1.88 Crore, as on the last date of previous financial year, i.e. FY 2019-20 or FY2020-21. In-principle sanction letter from the lending institutions/ banks of the Bidder, committing a Line of Credit for a minimum amount of INR 2.35 Crore, towards meeting the working capital requirement of the project quoted under this RfS. Such letter can also be obtained by the Affiliate(s) of the Bidder.
30 | ITB Section - III | 47 | 23a. |  | Contractual
31 | Bid Evaluation And Selection of Project | 60 | 2.B.3 | In this step, evaluation will be carried out for each Project based on tariff quoted byBidders. Levelised Tariff has to be less than INR 3.41/ kWh. Those bids wherethe tariff quoted is more than INR 3.41/ kWh, shall be summarily rejected. | Contractual | In this step, evaluation will be carried out for each Project based on tariff quoted byBidders. Levelised Tariff has to be less than INR 3.34/ kWh. Those bids wherethe tariff quoted is more than INR 3.34/ kWh, shall be summarily rejected.
32 | Bid Evaluation And Selection of Project | 60 | 2.B.8 | Ranking of bidders after Financial Bid Evaluation: Following illustrates an example of ranking of bidders after financial bid opening and evaluation Bidder Submitted Financial Bid Ranking B1 3.10 (Tariff in ₹/ kWh) L1 B2 3.20 (Tariff in ₹/ kWh) L2 B3 3.25 (Tariff in ₹/ kWh) L3 B4 3.25 (Tariff in ₹/ kWh) L3 B5 3.30 (Tariff in ₹/ kWh) L4 B6 3.31 (Tariff in ₹/ kWh) L5 B7 3.39 (Tariff in ₹/ kWh) L6 B8 3.40 (Tariff in ₹/ kWh) L7 B9 3.41 (Tariff in ₹/ kWh) L8 | Contractual | Ranking of bidders after Financial Bid Evaluation: Following illustrates an example of ranking of bidders after financial bid opening and evaluation Bidder Submitted Financial Bid Ranking B1 3.10 (Tariff in ₹/ kWh) L1 B2 3.20 (Tariff in ₹/ kWh) L2 B3 3.25 (Tariff in ₹/ kWh) L3 B4 3.25 (Tariff in ₹/ kWh) L3 B5 3.30 (Tariff in ₹/ kWh) L4 B6 3.31 (Tariff in ₹/ kWh) L5 B7 3.32 (Tariff in ₹/ kWh) L6 B8 3.33 (Tariff in ₹/ kWh) L7 B9 3.34 (Tariff in ₹/ kWh) L8
33 | Section IV | 64 | 2 | BBMB will sign PPA with the Successful Bidder and erection, commissioning and maintain the LILO connection to facilitate the evacuation of power from Gantry of 66 KV FSPV Substation to the 66 KV HPSEB line as set forth in the RFS document. In addition to this BBMB shall.... | Technical | BBMB will sign PPA with the Successful Bidder. The erection commissioning & maintenance of the BBMB line for the power evacuation from Gantry of FSPV power plant till the 33kv/66Kv BBMB substation at 33 kV level will be in the scope of BBMB as set forth in the RFS document. In addition to this BBMB shall....
34 | Annexure - A | 98 | 2 (a) (viii) | Outdoor 66 kV switchgear panels including Vacuum Circuit Breakers, Current Transformers, Voltage Transformers, Relays and other accessories for complete protection at the point of interconnection. | Technical | Outdoor 33 kV switchgear panels including Vacuum Circuit Breakers, Current Transformers, Voltage Transformers, Relays and other accessories for complete protection at the point of interconnection.
35 | Annexure A | 98 | 2(ix) | Erection, Commissioning and Maintenance of FSPV substation including 66 KV bay for evacuation of power from FSPV Power Plant shall be carried out by SPD. Note: The Power from the FSPV power plant shall be evacuated at 66KV gantry of FSPV substation to 66 KV HPSEB line through a dedicated transmission Line (i.e. LILO connection). Erection, commissioning and maintenance of dedicated Transmission line (LILO connection) from existing 66 kV HPSEB line upto 66 KV Gantry of Floating solar substation shall be in the scope of BBMB | Technical | Erection, Commissioning and Maintenance of FSPV substation including 33 KV bay for evacuation of power from FSPV Power Plant shall be carried out by SPD. Note: The Power from the FSPV power plant shall be evacuated at 33KV gantry of FSPV substation to 33 KV/66KV BBMB substation through a dedicated transmission Line. Erection, commissioning and maintenance of dedicated Transmission line from 33 KV Gantry of Floating solar substation till 33KV/66KV BBMB substation shall be in the scope of BBMB. The dedicated transmission line shall be built by BBMB as per the prevailing CERC regulations/CEA guidelines and applicable Indian grid code (IGC) including its amendments/clarifications issued thereon.
36 | Annexure A | 99 | 3 | Further, PV Modules should have been included in the ALMM list as per MNRE Approved Models and Manufacturers of Solar Photovoltaic Modules (Requirements for Compulsory Registration) Order, 2019. | Technical | Further, PV Modules should have been included in the ALMM list as per MNRE Approved Models and Manufacturers of Solar Photovoltaic Modules (Requirements for Compulsory Registration) Order, 2019 including amendments and clarifications issued thereof.
37 | Annexure A | 105 | 15 | Indicative site layout image | Technical | Revised indicative site layout image is enclosed at Annexure to RfS
38 | Appendix-A1 | 106 | 8 | SPD shall ensure Connectivity of the FSPV project upto the delievery point connected with LILO network of BBMB. Connectivity report as per the Appendix - A3. | Technical | SPD shall ensure Connectivity of the FSPV project upto the delievery point connected with 33kV/66kV BBMB substation through a dedicated transmission line. Connectivity report as per the Appendix - A3.
39 | ITB Section - III | 124 | 11.1 | Bidders selected by SECI based on this RfS shall submit Performance Guarantee for a value @ INR 2,70,00,000 (Two Crores Seventy Lakhs Only) within 30 days of issuance of Letter of Award (LoA) or before signing of PPA, whichever is earlier. It may be noted that successful Bidders shall submit the Performance Guarantee according to the Format 7.3B with a validity period of 27 months from the Effective Date of the PPA. On receipt and after successful verification of the total Performance Bank Guarantee in the acceptable form, the BG submitted towards EMD shall be returned by SECI to the successful Bidder. Non submission of PBG within the above mentioned timelines shall be treated as follows:................. | Contractual | Bidders selected by SECI based on this RfS shall submit Performance Guarantee for a value @ INR 2,03,00,000 (Two Crores Three Lakhs Only) within 30 days of issuance of Letter of Award (LoA) or before signing of PPA, whichever is earlier. It may be noted that successful Bidders shall submit the Performance Guarantee according to the Format 7.3B(PBG) with a validity period of 27 months from the Effective Date of the PPA. On receipt and after successful verification of the total Performance Bank Guarantee in the acceptable form, the BG submitted towards EMD shall be returned by SECI to the successful Bidder. Non submission of PBG within the above mentioned timelines shall be treated as follows:.................
40 | Form & Formats | Seriol No. 6 of Amendment 01 | Format 7.12 | Format 7.12 - DECLARATON FOR RESTRICTION ON PROCUREMENT FROM CERTAIN COUNTRIES | Contractual | Format 7.12 - ADDITIONAL DECLARATON FOR RESTRICTION ON PROCUREMENT FROM CERTAIN COUNTRIES (attached
41 | Forms & Formats | Format 7.13 |  | New Format 7.13 | Contractual | Format 7.13 - Undertaking to be submitted as part of Disclosure for Shareholding less than 26 Percentage (As attached Annexure to Amendment 02)
42 | Forms & Formats | Format 7.3C |  | New Format 7.3C | Contractual | Format 7.3C - Bid Security Decleration (As attached Annexure to Amendment 02)
43 | Forms & Formats | Format 7.7 |  | Existing Format 7.7 (Format for Disclosure) | Contractual | Amended Format 7.7 (Format for Disclosure) attached at Annexure to Amendment 02
44 | Whole Tender Document |  |  | Address of Solar Energy Corporation of India Limited as below - Solar Energy Corporation of India :Limited, D- 3, 1st Floor, Wing - A, Prius Platinum Building, District Centre, Saket, New Delhi - 110 017 Tel: 011 - 71989200, Fax: 011 - 71989243 | Contractual | For further reference under this tender document, Address of Solar Enegy Corporation of India Limited (SECI) is to be used as mention below - Solar Energy Corporation of India Limited 6th Floor, Plate - B, NBCC Office Block Tower – 2, East Kidwai Nagar, New Delhi - 110 023
45 | Section - III (ITB) |  | 27.4 |  | Contractual
46 | Appendix A1, Commissioning Procedure, Documents to be submitted to BBMB/SECI | 106 | 21 | SPD is permitted to schedule the Commissioning of the Project in full or part as per the commissioning procedure elaborated in Clause No. 16, Section-II, ITB of RfS Documents. | Technical | SPD is permitted to schedule the Commissioning of the Project in full as per Article 9 of the PPA and as per the commissioning procedure elaborated in Clause No. 16, Section-II, ITB of RfS Documents.
47 | Appendix A2, INSTALLATION REPORT | 109 | XII | Date of Installation of Part / Full Capacity (as per Capacity proposed to be Commissioned) | Technical | Date of Installation of Full Capacity (as per Capacity proposed to be Commissioned)
48 | Qualification Requirement SECTION - | 56 | C5 | A Company/ Consortium would be required to submit annual audited accounts for the last financial year, i.e. FY 2018-19, along with net worth, annual turnover and PBDIT certificate (as applicable) from a practicing Chartered Accountant/ Statutory Auditor to demonstrate fulfilment of the criteria. In case of foreign companies, the Bidders shall be required to submit the annual audited accounts for the last respective financial year as per the general norm in the country where the Bidder or its Affiliate(s) is/ are located. | Financial | A Company/ Consortium would be required to submit annual audited accounts for the last financial year, i.e. FY 2019-20 or FY 2020-21, along with net worth, annual turnover and PBDIT certificate (as applicable) of FY 2019-20 or FY 2020-21 from a practicing Chartered Accountant/ Statutory Auditor to demonstrate fulfilment of the criteria. In case of foreign companies, the Bidders shall be required to submit the annual audited accounts for the last respective financial year as per the general norm in the country where the Bidder or its Affiliate(s) is/ are located.
49 |  |  |  | General Statement
If the Project is ready but the necessary power evacuation /LILO connection /transmission infrastructure is not ready, leading to offtake constraint
The normative CUF of 19% (Nineteen per cent) or committed CUF, whichever is lower, for the period of grid unavailability, shall be taken for the purpose of calculation of generation loss. Corresponding to this generation loss, the excess generation by the SPD in the succeeding 3 (three) Contract Years, shall be procured by BBMB at the PPA tariff so as to offset this loss.
Transmission Constraint
Provision for Generation Compensation
If the Project is ready but the necessary power evacuation /BBMB line for conniting the FSPV Plant s/s to 33 kv/66kv BBMB s/s /transmission infrastructure is not ready, leading to offtake constraint
The normative CUF of 19% (Nineteen per cent) or committed CUF, whichever is lower, for the period of grid unavailability, shall be taken for the purpose of calculation of generation loss. Corresponding to this generation loss, the excess generation by the SPD in the succeeding 3 (three) Contract Years, shall be procured by BBMB at the PPA tariff so as to offset this loss.
Transmission Constraint
Provision for Generation Compensation