## FIN-2
Form FIN-2 Summary of Costs (For 100 MW (AC) FSPV Project at Getalsud, Jharkhand)
Item | Cost (INR) | GST Amount (INR) | Total Cost (INR)
{Consultant must state the proposed Costs in accordance with ITC 16.4 of the Data Sheet; delete columns which are not used}
Cost of the Financial Proposal including:
(1) Remuneration {The Remuneration mentioned under Cell No D13 here should match the total amount of Remuneration under Form FIN-3}
1(A) Mobilization of adequate manpower at site post site handover meeting |  |  | 0
1(B) Design Review Completion of Solar AC and DC component review 50 % of Major Drawing List (MDL) including Plot Plan, SLD, GA, Electrical LT side design. |  |  | 0
1(C) Design Review Completion of Solar AC and DC component review Review Balance of MDL |  |  | 0
1(D) Design Review Component of Floating System review 100% of design clearance |  |  | 0
1(E) Site Supervision including factory Inspection Equated monthly payments for each of 18 months |  |  | 0
1(F) Site Supervision including factory Inspection Project Commissioning and completion of punch point items and project Commercial Operation Date (COD) |  |  | 0
1(G) Site Supervision during O&M stage |  |  | 0
Grand Total (1) Remuneration |  |  | 0
(2) Reimbursable {The Reimbursable mentioned under Cell No D22 here should match the total amount of Remuneration under For FIN-4}
2(A) Mobilization of adequate manpower at site post site handover meeting |  |  | 0
2(B) Design Review Completion of Solar AC and DC component review 50 % of Major Drawing List (MDL) including Plot Plan, SLD, GA, Electrical LT side design. |  |  | 0
2(C) Design Review Completion of Solar AC and DC component review Review Balance of MDL |  |  | 0
2(D) Design Review Component of Floating System review 100% of design clearance |  |  | 0
2(E) Site Supervision including factory Inspection Equated monthly payments for each of 18 months |  |  | 0
2(F) Site Supervision including factory Inspection Project Commissioning and completion of punch point items and project Commercial Operation Date (COD) |  |  | 0
2(G) Site Supervision during O&M stage |  |  | 0
Grand Total (2) Reimbursable |  |  | 0
Total Cost of the Financial Proposal including GST: (1) + (2) : {Should match the amount in Form FIN-1} |  |  | 0

## FIN-3
Form FIN-3 BREAKDOWN OF REMUNERATION (For 100 MW (AC) FSPV Project at Getalsud, Jharkhand)
A. Remuneration When used for Lump-Sum contract assignment, information to be provided in this Form shall only be used to demonstrate the basis for the calculation of the Contract’s ceiling amount; to calculate applicable taxes at contract negotiations; and, if needed, to establish payments to the Consultant for possible additional services requested by the Client. This Form shall not be used as a basis for payments under Lump-Sum contracts.
No. | Name | Position (as in TECH-6) | Person-month Remuneration Rate | Time Input in Person/Month (from TECH-6) | Total in Rs.
Key Experts
K-1
K-2
K-3
K-4
K-5
K-6
K-7
K-8
K-9
K-10
K-11
K-12
K-13
K-14
K-15
Non-Key Experts
N-1
N-2
N-3
N-4
N-5
N-6
N-7
N-8
N-9
N-10
N-11
N-12
N-13
N-14
N-15
| Total Cost (Rs.) |  |  |  | 0
The total amount of Remuneration under this Form FIN-3 should match with the Remuneration amount mentioned under Cell No D13 of Form FIN 2. Consultants may add further line items in this sheet, if required.

## FIN-4
FORM FIN-4 BREAKDOWN OF REIMBURSABLE EXPENSES (For 100 MW (AC) FSPV Project at Getalsud, Jharkhand)
B. Reimbursable Expenses When used for Lump-Sum contract assignment, information to be provided in this Form shall only be used to demonstrate the basis for calculation of the Contract ceiling amount, to calculate applicable taxes at contract negotiations and, if needed, to establish payments to the Consultant for possible additional services requested by the Client. This form shall not be used as a basis for payments under Lump-Sum contracts
No. | Type of Reimbursable Expenses | Unit | Unit Cost | Quantity | In Indian Rupees (Rs.)
1 | {e.g., Per diem allowances**} | {Day}
2 | {e.g., International flights} | {Ticket}
3 | {e.g., In/out airport transportation} | {Trip}
4 | {e.g., Communication costs between Insert place and Insert place}
5 | {e.g., reproduction of reports}
6 | {e.g., Office rent}
7 | {Training of the Client’s personnel – if required in TOR}
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
| Total Cost (Rs.) |  |  |  | 0
Legend: “Per diem allowance” is paid for each night the expert is required by the Contract to be away from his/her usual place of residence. Client can set up a ceiling.
The total amount of Reimbursable under this Form FIN-4 should match with the Reimbursable amount mentioned under Cell No D22 of Form FIN 2. Consultants may add further line items in this sheet, if required.