## Pre Bid Queries
Selection of Agency for Outright Purchase or Lease of 800 acres of land for development of 200 MW SPV Project in MP
Tender No.: SECI/C&P/MI/00/05/2024-25
S. No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Queries | Category (Finance/Technical/Contractual) | Clarifications
1 | I | 9 of 156 | 6 under Bid Information Sheet | Completion/ Contract Period | The total timeline for the entire Scope of Work is given as 6 Months from the date of Signing of the Agreement i.e. D0. However, we wish to highlight that to Aggregate 800 Acres Land along with Obtaining Connectivity at STU is not at all feasible in 6 months duration. We would like to highlight the following critical factors contributing to the need for an extension: 1. Land Data Collection: In the state of Madhya Pradesh, land data is not available online. This necessitates the physical collection of documents from various Tehsil offices. The process of retrieving these documents is time-consuming and is estimated to take approximately 1 to 1.5 months. The physical nature of this task, coupled with the potential for delays in obtaining the required documents, makes it challenging to meet the original timeline. 2. Legal Due Diligence: Following the collection of land documents, a thorough legal due diligence (TSR) will be carried out by our legal team. This phase is expected to take at least 1 month. Additionally, verification and review by your legal representatives will add another month to this process. These steps are crucial to ensure compliance and to address any legal concerns, thereby extending the overall timeline. 3. Pre Non-Agricultural (NA) Conversion: In Madhya Pradesh, obtaining Pre Non-Agricultural (NA) Conversion is a prerequisite for registering lease deeds. The approval process for the NA application is time-intensive and can take between 1 to 2 months. Only after the NA approval can we proceed with the execution of the lease deed or sale deed. This step is vital for securing land rights and legal formalities but significantly impacts the project timeline. Given these factors, we respectfully request an extension of the completion/contract period from the current 6 months to at least 12 months. This adjustment will provide the necessary time to address the complexities involved and ensure that all requirements are met thoroughly and effectively | Contractual | Kindly refer to Amendment 01.
2 | II | 15 of 156 | 2 | The payment of land cost / lease rent shall be made by Solar Energy Corporation of India Limited directly in the account of land owners. Stamp duty and registration charges will be paid directly by Solar Energy Corporation of India Limited. | As referenced in the existing Clause, we request the inclusion of the following additional provisions to streamline the process: a) Sale Deed/ Lease Deed Execution and Land Cost Payment: The Bidder shall be responsible for executing the Sale Deed or Lease Deed in the name of SECI. Additionally, the Bidder will manage the payment of Land Cost or Lease Rent directly to the farmers on behalf of SECI. To facilitate a more efficient reimbursement process, the Bidder will be entitled to raise an invoice for reimbursement once a specified benchmark—either 10% or 15% of the total land quantum—has been achieved. This approach is designed to accelerate the process and ensure timely financial management. b) Stamp Duty and Registration Charges: For expenses related to Stamp Duty and Registration Charges, the Bidder will pay these costs directly to the relevant Government departments. The Bidder will then be eligible to claim reimbursement for these expenses based on the actual amounts paid. This provision will ensure that the Bidder is compensated for the administrative costs associated with the registration process. | Contractual | Kindly refer to Amendment 01.
3 | II | 16 of 156 | 2 | The bidder shall submit a legible copy of land map marked with individual survey numbers for all the offered land parcel(s). The bidder shall also submit a schedule of survey numbers along with area of respective survey numbers. | Kindly clarify the on a couple of important points concerning the land parcel map to be submitted as part of our bidding process: a) Deviation in Land Parcel Map: It is understood that the map we provide during the bidding stage may show some variations from the actual conditions on the ground. Once the contract is awarded, will there be any obligations or requirements related to these deviations? Specifically, we need to understand if there will be any repercussions or if we need to make adjustments to align with the actual land conditions. b) Submission of Tentative Land Map: We have noted that online land data or maps are not available for the state of Madhya Pradesh. According to the tender clause, we are required to specify the individual survey numbers of the land parcels offered. Given this situation, is it permissible for us to submit a tentative map during the bidding stage? This tentative map would illustrate the proposed land shape for the 800 acres of land, though it may not have the precise survey numbers at this stage. | Technical | a) Kindly refer Clause 2(1)(xiv) of Section-II (Scope of Works and Technical Specifications) for change of land patches after award of the contract. b) The bidder may refer https://mpbhulekh.gov.in/ for online maps.
4 | II | 16 of 156 | 2 | After opening of technical bids, a site visit will be conducted. In case the land is not found to be technically suitable for development of Solar PV project, the bid will be rejected. | How will SECI assess whether the land provided by the bidder meets the technical requirements? Will SECI utilize a detailed checklist or set of criteria during the physical site visit to evaluate the land's suitability? If so, what specific factors will be considered in this checklist to ensure that the land meets all necessary technical standards for the project? | Technical | Suitability of the land will be assessed based on the factors which are not limited to the following. Undulation, Encroachment, Forest area, Access, Presence of boulders and water bodies, Presence of obstacles and structures that may impact the Solar plant, Transmission/Distribution line, Railway line, National/State Highway, Oil and gas pipelines, Bridges, Culverts, etc.
5 | II | 18 of 156 | 2 | Submission of third-party legal opinion w.r.t. clear title land status of land parcels / pockets. | Could you please clarify whether a bidder is allowed to obtain a third-party legal opinion from a registered lawyer who is not affiliated with the bidder's organization? Additionally, are there specific lawyers or law firms that must be consulted for this third-party legal opinion? | Contractual | Bidder is allowed to obtain third-party legal opinion from a registered lawyer not affiliated with the bidder's organization. Further no specific lawyers or law firms are required to be consulted for this third-party legal opinion.
6 | II | 20 of 156 | 2 | Identifying STU substation for inter-connection of Transmission Line and obtaining connectivity The bidder shall identify 220 kV State Transmission Utility (STU), i.e., Madhya Pradesh Power Transmission Company Limited (MPPTCL),substation nearest to the proposed land parcel(s) which has available evacuation capacity of minimum 200 MW for evacuation of 200 MW Solar PV power at 220 kV level. The bidder shall submit documentary proof from STU for availability of evacuation capacity at the identified substation. The bidder shall submit the coordinates of the identified substation and bay availability details in the Form XIV. Obtaining connectivity on behalf of Solar Energy Corporation of India Limited after award of the contract is in the scope of the Contractor. Application fee for connectivity application will be paid directly by Solar Energy Corporation of India Limited. All expenses relating to salary and allowances including statutory obligations like EPF &/ ESI etc. of the deployed labour shall be borne by the Contractor. | As specified in the clause, bidders are required to provide documentary proof from the State Transmission Utility (STU) confirming the availability of evacuation capacity at the designated substation. However, MPPTCL does not currently provide up-to-date data on their STU margin availability, with the most recent data available being from December 2023. Given this situation, how can bidders submit the required documentary proof as of the current date? Additionally, what specific type of documentary proof is required to demonstrate the availability of evacuation capacity? | Technical | Bidder may write to MPPTCL to get the details of availability of connectivity at the STU S/s under consideration. The terms and conditions of the tender document shall prevail.
7 | III | 26 of 156 | 4.3 | The Tender Processing Fee and EMD, if applicable is exempted for MSEs Vendors registered under NSIC/ Udyog Aadhaar/DIC Category only. To avail the exemption in Tender Processing Fee in case of consortium/ JV, all the members should be registered as MSEs Vendors under NSIC/ Udyog Aadhaar Category/DIC. | Kindly clarify whether MSME exemption will be allowed as per the general clause referred to by SECI in their IPP tenders. | Contractual | Exemption to MSE vendors for EMD and Tender Processing Fees is available in the with the mentioned clause.
8 |  |  |  |  | Can we get some SPV Arrangement in this tender? The general process would involve: 1. SPV Formation: The bidder can form an SPV specifically for the tender. This entity would handle the land aggregation, power evacuation, and other project-specific tasks. 2. Land Aggregation and Connectivity: The SPV would be responsible for aggregating the required land and obtaining connectivity for the project. This helps streamline the process and ensures that all project-related activities are handled under a single entity. 3. Transfer to SECI: After the SPV has achieved the necessary milestones (like land aggregation and connectivity), it can transfer the SPV to SECI or any other designated entity as per the tender requirements. This transfer process should be compliant with the tender's terms and conditions. | Contractual | The formation of SPV arrangement is permitted in the tender document. Kindly refer to Amendment 01.
9 |  | 102 | 5(II) |  | Page 102 - Clause 5.ii: Could you please clarify whether there is a maximum limit to the loss or damage resulting from a breach of duty by any employee? | Contractual | All the damages will be dealt in line with the "Section VII - Special Condition of Contracts Liquidated Damages (GCC clause 16)" of the tender document.
10 |  | 118 |  |  | 2. Page 118 - Liquidated Damages: We request a revision of the maximum limit for liquidated damages from 5% to 3%, as this percentage has been accepted by other PSUsfor similar projects. | Contractual | The terms and condition of the tender document shall prevail.
11 |  |  |  |  | Is there any provision for compensate on of crops to farmers in case of agriculture land. | Contractual | No
12 |  |  |  |  | If the land is available in parcels of 2 patches of diff erent district. Will it fulfil l the purpose. | Contractual | Given that both the land parcels qualify the basic conditions laid out in the tender document.
13 |  |  |  |  | What is the purpose of water table depth to be menti on in bid format, also let us know the authentic source to obtain this detail. | Technical | For construction, operation and maintenance of the Solar PV plant, ground water will be utilized. So, it is essential to know the depth of water table at the proposed site. The bidder may collect water table data from state or central government water resource departments.
14 |  |  |  |  | 220kv STU availability is low in MP (avg one per district) , in this case 132kv or lower STU is feasible, will it fulfil l the purpose. | Technical | Only STU connectivity with 220 kV is acceptable.
15 |  |  |  |  | In case of bay capacity is not available, what is the total area required for new Bay to be construct and is it the scope of bidder or SECI to coordinate with MP transmission company. | Technical | Area required for new bay shall not be less than the area occupied by the existing 220 kV bay in the proposed STU Substation. Coordination with MPPTCL for allocation of land required for bay construction shall be in the scope of the Contractor.
16 |  |  |  |  | Distance to STU is also not feasible, can it be greater than 40-50km. | Technical | Kindly refer to Amendment 01.
17 |  |  |  |  | Coordinate on with STU related to BAY availability / evacuate on capacity will be done by Bidder or SECI. | Technical | Coordination with STU for evacuation capacity and bay availability shall be in the scope of the Contractor.
18 |  |  |  |  | Is the transmission line connect vity from STU to Land Parcels is scope of Bidder or SECI. | Technical | Obtaining connectivity at the STU substation on behalf of SECI is in the scope of the Contractor. Laying of transmission line from the proposed land to the STU substation is not in scope of the Contractor.
19 |  |  |  |  | SECI will provide ROW for laying of transmission line. | Technical | Laying of transmission line is not in the scope of the Contractor.
20 |  |  |  |  | O&M of transmission line is in bidder scope, pl specify for how many years. | Technical | O&M of transmission line is not in the scope of the Contractor.
21 |  |  |  |  | As per tender document, JV/consortia um is not allowed but in clause 37.2 it is menti owned that JV cane done if both have MSE carta fi coati on, its contradictory. | Contractual | Exemption to MSE vendors for EMD and Tender Processing Fees is available in the with the mentioned clause.
22 |  |  |  |  | The rate menti owned in clause 31.3.3 for EBV calculate on are illustrate vee or freeze for party cular work tobe menti on in SoR. | Contractual | The formula mentioned under the clause 31.3.3 of the tender document will be strictly used for calculating the Evaluated Bid Value without any deviation, as also highlighted in the Schedule of Rate sheet of the tender document.
23 | 4 | 26 | 4.3 | COST OF BIDDING & TENDER PROCESSING FEE | Udyog Aadhaar Memorandum - MH33D0232055 will this be exempted from | Contractual | Exemption to MSE vendors for EMD and Tender Processing Fees is available in the with the mentioned clause.
24 | 14 | 39 | 14.1 | EARNEST MONEY DEPOSIT(EMD) | tender processing fees and EMD? | Contractual | Query not clear.
25 | 37 | 61 | 37.1 | PUBLIC PROCUREMENT POLICY FOR MICRO AND SMALL ENTERPRISES (MSEs) |  | Contractual | Query not clear.
26 | 1 | 92 | 1.1 | GENERAL ELIGIBILITY CRITERIA |  | Contractual | Query not clear.
27 | [5 empty] | Contractual | Query not clear.
28 | 5 | 94 | 1.3.1 | The Minimum Average Annual Turnover (MAAT) of the Bidder in the last three financial years (i.e. FY 2021-22, 2022-23 & 2023-24) should be INR 4,42,00,000.00 (Indian Rupees Four Crores Forty-Two Lakhs only). | My company doesn't meet this eligibility criteria so kindly confirm | Contractual | The terms and condition of the tender document shall prevail.
29 |  |  | 1.3.3 | The bidder should have a minimum Working Capital of INR 2,76,00,000/- (Indian Rupees Two Crores Seventy-Six lakhs only) as per the last audited financial statement. | if there's any alternative for participation | Contractual | The terms and condition of the tender document shall prevail.
30 | TECHNICAL ELIGIBILITY CRITERIA | 93 | 1.2.5 | The aerial distance between the nearest point of the land parcel(s) offered and the proposed STU substation shall not be more than 25 km. | Availability of 220 KV substation is limited hence this distance should be increased to 35 KM. | Technical | Kindly refer to Amendment 01.
31 | Services for Allied Works | 18 | IV | All the statutory charges other than stamp duty, registration charges, etc. shall be borne by the Contractor | Stamp duty charges, registration charges and lawyers cost should be paid by SECI directly to concerned lawyer/agency | Technical | Kindly refer Clause 2(1)(iii) of Section-II (Scope of Works and Technical Specifications). Stamp duty and registration charges will be paid directly by Solar Energy Corporation of India Limited. All the statutory charges other than stamp duty, registration charges, etc. shall be borne by the Contractor. Lawyers cost shall be paid by the Contractor. The terms and conditions of the tender document shall prevail.

## Amendment-1
Tender No.: SECI/C&P/MI/00/05/2024-25
Selection of Agency for Outright Purchase or Lease of 800 acres of land for development of 200 MW SPV Project in MP
S. No. | Section | Sub-Section | Page No. | Clause | Original Version | Amendment
1 | II Scope of Work / Technical Specification | 2. Detailed Scope of Works | 15 of 156 | 2 (1) iii. | The payment of land cost / lease rent shall be made by Solar Energy Corporation of India Limited directly in the account of land owners. Stamp duty and registration charges will be paid directly by Solar Energy Corporation of India Limited. | 2 (1) iii (a) The payment of land cost / lease rent shall be made by Solar Energy Corporation of India Limited directly in the account of land owners. Stamp duty and registration charges will be paid directly by Solar Energy Corporation of India Limited. (b) Additionally the agency can pay the land cost (in case of outright purchase) or upfront lease rent (in case of annual lease) directly to the land owners on behalf of SECI and the same will be reimbursed to the agency on back to back basis. Further the expenses related to stamp duty and registration charges, the agency can pay these costs directly to the relevant government departments and the same will be reimbursed to the agency on back to back basis.
2 | II Scope of Work / Technical Specification | Identifying STU substation for inter-connection of Transmission Line and obtaining connectivity | 20 of 156 | {4} | Add following to the existing clause | The availability of connectivity is the most vital component of the tender, which is to be established by the successful agency at all point during the tendering process and till the stage of award of Contract. Agency having established the connectivity availability at the time of bidding, but failing to establish such connectivity at the time of actual award will not be consider as the successful agency and in such a situation the award placed will be withdrawn.
3 | III Instructions to Bidders | Evaluation of Financial Part (Second Envelope) | 55 of 156 | 31.3 | Add following to the existing clause | Provision for L1 Matching: A. In case the successful agency fails to demonstrate the connectivity at the time of actual award, such agency will be declared as the unsuccessful agency and the award placed will be withdrawn. In such a situation, the award will be offered to the L2 agency, having established the successful connectivity availability and subject to matching the L1 price. The process of L1 price matching along with the connectivity availability will continue so on till the successful agency is selected.
4 | III Instructions to Bidders | Evaluation of Financial Part (Second Envelope) | 56 of 156 | 31.3.3 | In case of lease, Effective Land Cost = (18.31 x Annual Lease Rent quoted by the bidder including GST and excluding stamp duty & registration charges) + Stamp duty & Registration charges quoted by the bidder. | In case of lease, Effective Land Cost = (18.31 x First Year Lease Rent quoted by the bidder including GST and excluding stamp duty & registration charges) + Stamp duty & Registration charges quoted by the bidder. Annual escalation on lease rent = 3%
5 | III Instructions to Bidders | Signing of Contract Agreement | 58 of 156 | 34 | Add following to the existing clause | In case of Lease Deed, the Lease Agreement to be signed is attached as Annexure 1 to the Amendment 01.
6 | V Qualifying Requirements | 1.2 Technical Eligibility Conditions | 93 of 156 | 1.2.5 | The aerial distance between the nearest point of the land parcel(s) offered and the proposed STU substation shall not be more than 25 km. | The aerial distance between the nearest point of the land parcel(s) offered and the proposed STU substation shall not be more than 30 km.
7 | I Invitation for Bids (IFB) | Completion / Contract Period | 9 of 156 | 6 | Zero Date (D0) will be the date of signing of Contract Agreement (CA) or Notice to Proceed (NTP), whichever is later. NTP (if applicable) will be provided by SECI in the shortest possible time and all contractual obligations for the project will be started from the date of Notice to Proceed (NTP). The total timeline of 06 months is bifurcated as follows: | Zero Date (D0) will be the date of signing of Contract Agreement (CA) or Notice to Proceed (NTP), whichever is later. NTP (if applicable) will be provided by SECI in the shortest possible time and all contractual obligations for the project will be started from the date of Notice to Proceed (NTP). The total timeline of 08 months is bifurcated as follows:
8 | I Invitation for Bids (IFB) | Completion / Contract Period | 9 of 156 | 6
9 | IV Bid Data Sheet | Contract Performance Security | 87 of 156 | 2 | 15.1 Against the contract of the project, within 30 (Thirty) days from the issuance of the CA/NTP from SECI, the successful Bidder shall furnish an unconditional and irrevocable Contract Performance Security as per Format attached and which shall be for 3% (three) of the sum of the value of line item D, E, F and G of the Schedule of Rate and shall be valid up to 09 (nine) months {06 months of total completion period + 03 months additional} from the date of signing of Contract Agreement or Notice to Proceed (whichever is later). | 15.1 Against the contract of the project, within 30 (Thirty) days from the issuance of the CA/NTP from SECI, the successful Bidder shall furnish an unconditional and irrevocable Contract Performance Security as per Format attached and which shall be for 3% (three) of the sum of the value of line item D, E, F and G of the Schedule of Rate and shall be valid up to 11 (Eleven) months {08 months of total completion period + 03 months additional} from the date of signing of Contract Agreement or Notice to Proceed (whichever is later).
10 | VII Special Conditions of Contract | Formation of SPV Arrangement post Award | 119 of 156 | 5 (GCC clause 17) | Add following to the existing clause | For information related to SPV Formulation post award by the successful agency, please refer to Annexure 2 to the Amendment 01.
11 | VII Special Conditions of Contract | Payment Terms | 116 of 156 | 3 (GCC clause 15) | The payment of land cost / lease rent (i.e., payment against the line item A and B) shall be made by Solar Energy Corporation of India Limited directly in the account of land owners. Stamp duty and registration charges will be paid directly by Solar Energy Corporation of India Limited. | The payment of land cost / lease rent (i.e., payment against the line item A and B) shall be made by Solar Energy Corporation of India Limited directly in the account of land owners. Stamp duty and registration charges will be paid directly by Solar Energy Corporation of India Limited. Additionally the agency can pay the land cost (in case of outright purchase) or upfront lease rent (in case of annual lease) (i.e., payment against the line item A and B) directly to the land owners on behalf of SECI and the same will be reimbursed to the agency on back to back basis. Further the expenses related to stamp duty and registration charges, the agency can pay these costs directly to the relevant government departments and the same will be reimbursed to the agency on back to back basis.
12 | SOR | - | - | - | Revised Schedule of Rates | New Schedule of Rates as attached has been added which will supersede the earlier SOR. Bidders quoting in the old SOR will be summarily rejected.
13 | General | - | - | - | General Information for Bidder's reference | It is to be mentioned that SECI has acquired in-principle connectivity on 5th Nov 2024, which shall remain valid until 5th November 2025, for evacuating 200 MW of solar power at the Badnawar Substation of MPPTCL. This development addresses a concern raised by potential bidders during pre-bid discussions about the availability of connectivity.