## Pre Bid Queries
“THE MANUFACTURING, TESTING, PACKING AND FORWARDING, SUPPLY AND TRANSPORTATION OF 260 MWP DOMESTICALLY MANUFACTURED SOLAR PV MODULES WITH DOMESTICALLY MANUFACTURED SOLAR CELLS”
Tender No : SECI/C&P/OP/11/018/2024-25
Sl. No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Queries | Category (Finance/Technical/Contractual) | Clarifications
1 | SoS & TS | 6 of 19 | 3 | The PV Module dimensions at the time of Supply shall be fixed as per details provided in Form T-01 submitted along with the bid | Kindly clarify whether the Solar Module supplied under this Tender shall be installed on Tracker or shall be Fixed-Mount (Tilt)? | Technical | The Module procured under this tender will be fixed mounted.
2 | SoS & TS | 7 of 19 | 4.5 | The anodization thickness shall be 15 micron (12 micron in case of 6005 Grade Aluminium). | The Anodization Thickness will be 15Micron or is it Minimum Thickness of 15micron. | Technical | The specifications provided are the minimum requirement. Bidder may propose greater anodization thickness. Please refer S. No. 1 of Amendment 1.
3 | SoS & TS | 7 of 19 | 4.7 | Each PV Module shall be provided with a RFID tag (This can be inside or outside the laminate, but must be able to withstand harsh environmental conditions). | Clarify whether RFID Readers also need to be supplied? If yes, how many? | Technical | 5 No. RFID tag readers shall be provided. Please refer S. No. 2 of Amendment No. 1.
4 | SoS & TS | 9 of 19 | 7.1 | The cells used for module making shall be free from all defects like edge chipping, breakages, printing defects, discoloration of top surface etc. Only Class A solar cell shall be used. | Clarify whether any classification exists to define Class A Solar Cell? Provide the necessary quality document (QAP Solar Cell) for the same meeting the expectation of SECI. | Technical | It is clarified that categorization of solar cells as Class A/Grade A is an industry standard classification implying that cells have no visual defects, lack chips, cracks, and scratches and meet the performance standards. The material acceptance/rejection criteria shall be approved by the Employer as per the PV Module QAP submitted by the Supplier to SECI, prior to manufacturing.
5 | SoS & TS | 3 of 19 | 1.1 | The scope of supply includes Manufacturing, Testing, Packing and Forwarding, Transportation to Site and Unloading of domestically manufactured Solar PV Modules with domestically manufactured solar cells. Unloading of the consignment (i.e. PV Modules supplied under this Contract) shall be the responsibility of the Employer. | Request to remove "Unloading" from the scope of supply as it is in the scope of Employer. Or does it imply that Unloading scope will be of the Supplier and the Employer will only Supervise the unloading at Delivery Location? | Technical | Unloading of the PV modules supplied under this contract shall be responsibility of the Supplier. Please refer S. No. 16 of Amendment 1.
6 | SFF | 49 of 60 | Form F-21 | Certificate from the Module Manufacturer to the SPD regarding meeting of DCR norms under CPSU Scheme-Phase-II (On the letterhead of the Supplier) (To be submitted post award) | Is this Certificate still required when the Supplier is both a Solar Cell and Module Manufacturer? | Contractual | Yes, the form needs to be submitted as it is a certificate from Module Manufacturer to the SPD regarding meeting of DCR norms.
7 | SFF | 51 of 60 | Form F-22 | Certificate from the Cell Manufacturer to the Module manufacturer regarding meeting of DCR norms under CPSU Scheme-Phase-II (On the letter-head of the Cell Manufacturer) (To be submitted post award) | Is this Certificate still required when the Supplier is both a Solar Cell and Module Manufacturer? | Contractual | Yes, the form needs to be submitted as it is a certificate from Cell Manufacturer to the Module Manufacturer regarding meeting of DCR norms. In case of both the parties being same, the form may be accordingly submitted incorporating same name under the Cell and Module Manufacturer.
8 | SFF | 58 of 60 | Form F-25 | DECLATION REGARDING THE MANDATORY PROCUREMENT OF SOLAR MODULES FROM CLASS I LOCAL SUPPLIERS | More 50% of the Solar Module procured by SECI should have local content. Does this imply that after award of tender, whatever selling price has been determined based on e-RA result, more than 50% of the selling price should have local content? Kindly clarify? | Contractual | The local value addition needs to be calculated in line with the Ministry of New & Renewable Energy (MNRE) Order No 283/22/2019-Grid Solar Dated 23rd Sep 2020 for the Public Procurement and Department for Promotion of Industry and Internal Trade (DPIIT) Notification No. P-45021/2/2017-PP (BE-LI) dated 4th June, 2020 including any amendments.
9 | SoS & TS | 9 of 19 | 6.4 | The Supplier shall submit a detailed Manufacturing Quality Plan (MQP) for the PV Module with list of checks/tests performed during incoming material inspection, production, pre-dispatch and package. | Kindly clarify whether Supplier MQP will be approved as-is or there may be additional requirements which may be discussed after award of contract. | Technical | Supplier MQP will be submitted for the approval of the Employer post the Award of the Contract.
10 | SoS & TS | 12 of 19 | 5.2 | (ii) Visual Inspection and (iii) Electroluminescence (Not applicable for thin-film modules) | Kindly clarify whether Supplier QAP will be approved as-is or there may be additional requirements which may be discussed after award of contract. | Technical | Supplier MQP will be submitted for the approval of the Employer post the Award of the Contract.
11 | GPC | 11 of 44 | 13.1 | The time for supply as specified in the SPC is firm & final binding till the final supply. The Time(s) for supply specified in the SPC shall be extended if the Supplier is delayed or impeded in the Performance of any of its obligations under the Contract due to delay in fulfilment of obligations by the Owner or by the reason of any of occurrence of Force Majeure as provided in the Tender for Force Majeure. | Requesting to please include delay due to change in law as well. | Contractual | The terms and conditions of the tender document shall prevail. However, respective Change in Law matters will be dealt in line with the Change in Law clause of the GPC section of the tender document.
12 | GPC | 30 of 44 | 50.1 | The decision of the Engineer-in-Charge/Project Manager as to any question arising under this clause shall be final and conclusive. No additional time for Project completion shall be granted for undertaking such replacement/ rectification supply by Supplier. | Request to include that a independent third party inspection would be done in order to asses the quality of the goods supplied | Contractual | The terms and conditions of the tender document shall prevail.
13 | GPC | 29 of 44 | 45 | The Supplier shall refer the matter immediately in writing to the Engineer-in-Charge/Project Manager whose decision thereon shall be final and conclusive and no claim for losses alleged to have been caused by such discrepancies between instructions, doubts, or misunderstanding shall in any event be admissible. | Requesting to include that all instructions would be recorded in order to avoid dispute | Contractual | The terms and conditions of the tender document shall prevail. However, all such matter will be dealt in mutual consultation between the Project Manager from SECI and the Contractor.
14 |  |  | SPC 3 | he total timeline for Completion for the entire 260 MWp (DC) Solar PV Module Package in total shall be 12 (Twelve) Months from the Date of the Purchase Order/Contract Agreement or Notice to Proceed (NTP), whichever is later. Under the above-mentioned total timelines of 12 months, PV Modules including Mandatory Spares under the award shall be supplied by the supplier in staggered deliveries during the delivery window of 8 months from (D+120 to D+360) days. For the calculation of Liquidated Damages for the delays, if any, the total timelines of 12 months will be calculated. | Regarding the Liquidated Damages (LD), it is mentioned that LD will be applicable after 12 months. As discussed during the Pre-Bid meeting, the weekly/monthly delivery schedule will be mutually agreed upon. We would appreciate your clarification on the following points: 1. Will LD be applicable based on the lot-wise scheduled delivery dates? 2. In the event that there are delays in monthly supplies but the overall delivery is completed within the 12-month timeline, will LD still be applicable | Contractual | The LD will be applicable on the unexecuted supply calculated at the end of the 12 month Contract window. Clause 21 on the Liquidated Damages (LD) of the GPC also clarifies the same regarding the applicability of the LD on the unexecuted supplies.
15 | GPC | 26 of 44 | 42 | Change in Laws and Regulation | Requesting to please include the definition of Change in Law and what all factors/changes can be constituted as change in law | Contractual | The term Change in Law shall refer to the occurrence of any of the following events pertaining to this supply only after the date seven (7) days prior to the date of Bid submission, including (i) the enactment of any new law; or (ii) an amendment, modification or repeal of an existing law; or (iii) any change in the rates of any Taxes including any duties and cess or introduction of any new tax made applicable for setting up the project.
16 | QUALIFYING REQUIREMENTS (QR) | 80 | 1.2 | The Minimum Average Annual Turnover (MAAT) of the bidder in the last three financial years (i.e. FY 2021-22, 2022-23 & 2023-24) should be INR 224.75 Crores/- (Indian Rupees Two Hundred and Twenty-Four Crores and Seventy-Five Lakhs only). MAAT shall mean Revenue from Operations as incorporated in the profit & loss account excluding other income, e.g. sale of fixed assets. A summarized sheet of average turnover, certified by a practicing Chartered Accountant/Statutory Auditor should be compulsorily enclosed along with corresponding annual accounts. AND The net worth for the last financial year should be positive. “Net Worth” of the Biddeshall be calculated as per the Companies Act, 2013. AND The bidder should have a minimum Working Capital of INR 140.47 Crores (Indian Rupees One Hundred and Forty Crores and Forty-Seven Lakhs only) as per the last audited financial statement. If the bidder’s working capital is inadequate, the bidder should supplement this with a letter from the bidder’s bank, having net worth not less than INR 500 Crores, confirming availability of the line of credit for more than or equal INR 140.47 Crores (Indian Rupees One Hundred and Forty Crores and Forty-Seven Lakhs only) to meet the working Capital requirement of this particular Project. | We Request you to consider Minimum Average Annual Turnover (MAAT) of the bidder in the last three financial years (i.e. FY 2021-22, 2022-23 & 2023-24) should be INR 175 Crores/- (Indian One Hundred Seventy Five Crore Rupees Only) AND The net worth for the last financial year should be positive. “Net Worth” of the Bidde shall be calculated as per the Companies Act, AND The bidder should have a minimum Working Capital of INR 75 Crores (Indian Rupees Seventy Five Crores only) as per the last audited financial statement. If the bidder’s working capital is inadequate, the bidder should supplement this with a letter from the bidder’s bank, having net worth not less than INR 500 Crores, confirming availability of the line of credit for more than or equal INR 75 Crores (Indian Rupees Seventy Five Crores only) to meet the working Capital requirement of this particular Project. | Contractual | The terms and conditions of the tender document shall prevail.
17 | BID INFORMATION SHEET | 13 | H | INR 5,60,00,000.00 (Indian Rupees Five Crores and Sixty Lakhs Only) | In Standard Practice Departments consider EMD Rs. 1 Crore for 100MW so request you to keep EMD as per standard practice | Contractual | The terms and conditions of the tender document shall prevail.
18 | BID INFORMATION SHEET | 13 | I | 10% of the Total Project/Order Cost for a total period of 27 months. | As per Standard Practice department follows 5% of the Total Project/Order Cost or Rs.10,00,000 /Mw so request you to please consider the same | Contractual | The terms and conditions of the tender document shall prevail.
19 | GPC | 26 of 44 | 40.3 | Clause 40.3 states that "the Supplier shall arrange for loading, transportation & unloading of materials at project site at his own cost & risk." While Clause 1.1, SoS & TS, page 3 of 19 states that "unloading of the consignment (i.e. PV Modules supplied under this Contract) shall be the responsibility of the Employer." | Please clarify whether unloading of the PV module pallets at the project site is in Supplier or Employer scope of works. | Contractual | The unloading of the PV Modules at site is in the scope of the BoS Contractor. And the typographical error has been corrected, kindly refer to Amendment 01.
20 | SA-B | 4 of 7 | 4 | Parameters for Simulated Specific Production of first year. | The monthly ground albedo values have not been specified. Solargis database for the site location in Dhar shows an annual albedo of 0.17, which is considerably lower than PVsyst default of 0.20. Please specify the ground albedo values for a more accurate representation of the site. | Technical | Please refer to Sl. No. 10 and Sl. No. 11 of Amendment 1 for ground albedo value.
21 | SA-B | 4 of 7 | 4 | Parameters for Simulated Specific Production of first year. | Please specify the module height above ground that will be taken in PVsyst. | Technical | The minimum height of the lowest part of the PV Module shall be 500 mm above the ground. Please refer S. No. 11 of Amendment 1.
22 | SoS & TS | 3 of 19 | 1.5 | The Supplier shall submit PAN file of the PV Modules to be supplied (certified by an ILAC member signatory accredited laboratory) at the time of Bidding. | Please confirm how SECI will verify that the submitted 3rd party lab tested PAN file with the bid is for a DCR module of module made in India and cell made in India (e.g. not for a module made in India incorporating a cell made in China). | Technical | Please refer S. No. 7 of Amendment 1. DCR Compliance shall be verified from the https://solardcrportal.nise.res.in/ portal
23 | SoS & TS | 6 of 19 | 4.1.2 | "Glass/Glass Modules: Glass shall be heat strengthened with a TOC layer…" | Please confirm that you mean TCO, i.e. Transparent Conductive Oxide. | Technical | Yes. It is clarified that TCO is for Transparent Conductive Oxide.
24 | SoS & TS | 8 of 19 | 4.6 | Junction box with "4 sq.mm. copper cable of 1200 mm shall be provided." | In the case of thin film module, the cable shall be 2.5 sq.mm given the lower current compared to c-Si modules. Moreover, with a dual junction box design, one of the receptacles has an in-built PV connector while the other receptacle has a lead wire of 500 mm with PV connector; this is because leap frog wiring is not applicable to thin film modules. Please confirm. | Technical | Please refer S. No. 3 of Amendment 1.
25 | SoS & TS | 5 of 19 | 2.1 | IS/IEC 61701: 2011 for salt mist corrosion test. | Salt mist corrosion is tested to the newer edition i.e. IEC 61701:2020. The 2011 edition was “Withdrawn” by the IEC. Please confirm this newer edition shall be used. | Technical | Higher revision of standards specified are acceptable. Please refer Clause No. 2.1 of Technical Specifications
26 | SoS & TS | 5 of 19 | 2.1 | IS 17210:Part 1:2019 / IEC TS 62804-1:2015 for PID test. | PID test to 62804-1:2015 is for crystalline silicon. Thin film modules are tested to IEC 61215-2:2021, Clause 4.21 ‘Potential induced degradation test (PID)’. IEC 61215-1 Table 3 states that the test conditions for IEC 61215-2:2021 PID Test (MQT21) is to IEC TS 62804-1. Since test conditions in the two standards are the same, please confirm that IEC 61215-2:2021, Clause 4.21 can be used for thin film modules. | Technical | Please refer S. No. 4 of Amendment 1.
27 | SA-B | 4 of 7 | 4 | Parameters for Simulated Specific Production of first year. | Please confirm whether a grid power limitation of 200MW will be applied at the injection point in the PVsyst simulation. | Technical | Yes, grid power limitation of 200MW will be applied at the injection point in the PVsyst simulation.
28 | SA-B | 4 of 7 | 3 | In case of thin film modules, first year degradation shall be deducted from Simulated Specific production to arrive at final SPsim_P75 value. | Taking the first year degradation on the plant-level simulated specific production (on the "AC side") for thin film but on the module-level (on the "DC side") for crystalline silicon would be unfair on thin film technology, as the inverters and plant controllers can be clipping energy and reducing the loss for the crystalline silicon case. For treatment to be similar to cSi (where it is accounted for in the 'LID' parameter) we request accounting for first year degradation as a loss in the 'Module Quality' parameter of PVsyst. | Technical | In case of thin film modules, first year degradation shall be accounted as 'Module efficiency loss' in PVSyst simulation. Please refer to S. No. 8 and S. No. 9 of Amendment 1.
29 | ITB | 3 | 2.8 | +/- 10% of awarded capacity on the same price, terms, and conditions of the contract (234MWp - 286MWp). | Request SECI to confirm this at least 3 months prior to the respective dispatch schedule. | Contractual | The +-10% variation clause if exercised, will be communicated to the supplier at the time of placing the purchase order. "The Owner reserves the right to increase or decrease the quoted PV Module capacity by ± 10% at the time of placing of the order on the same price, terms, and conditions of the contract."
30 | ITB | 3 | 2.9 | SECI reserves the right to order up to additional 10% of awarded PV Module capacity on the same price, terms and conditions of the contract. | Request SECI to confirm this at least 3 months prior to the respective dispatch schedule. | Contractual | The +-10% variation clause if exercised, will be communicated to the supplier at the time of placing the purchase order. "The Owner reserves the right to increase or decrease the quoted PV Module capacity by ± 10% at the time of placing of the order on the same price, terms, and conditions of the contract."
31 | SPC | 7 | 12 | The supplier shall arrange for removal of the rejected item(s) within 15 days from the date of notification. In the event, the supplier fails to lift the materials within the said 15 days, the Owner shall be at liberty to dispose of such rejected item(s) in any manner as he may think fit and recover all the expenses from the Supplier. | Request SECI to exclude the disposal of modules from supplier scope. | Contractual | The terms and conditions of the tender document shall prevail.
32 | Annexure to BDS | 4,5 | 1.3 | The Minimum Average Annual Turnover (MAAT) of the bidder in the last three financial years (i.e. FY 2021-22, 2022-23 & 2023-24) should be INR 224.75 Crores/ AND The net worth for the last financial year should be positive. “Net Worth” of the Bidder shall be calculated as per the Companies Act, 2013. AND The bidder should have a minimum Working Capital of INR 140.47 Crores (Indian Rupees One Hundred and Forty Crores and Forty-Seven Lakhs only) as per the last audited financial statement. | SECI to re-confirm if Calendar Year financials will be accepted as allowed in the previous RFP. | Contractual | As mentioned, only Financial Year statements will be accepted.
33 | GPC | 26 | 41 | During monsoon and other period, it shall be the responsibility of the Supplier to bear all the extra cost incurred for completing the supply as per the schedule. | Request SECI to not transfer risk and cost of site preparation and access to module supplier. Supplier scope is to deliver modules. Typically it’s the EPC contractor/owners responsibility to provide access and ensure site is in suitable condition for movement of trucks and receiving materials. | Contractual | The terms and conditions of the tender document shall prevail. However, SECI will ensure the site in suitable condition before accepting the Module delivery at site.
34 | Form F-21/22 | 51 of 60 |  | Form F-21 and F-22 are to be submitted post award. | Please confirm how SECI will verify that the module make and model proposed in the bid is DCR compliant during bid evaluation stage, prior to award. | Contractual | During the evaluation stage bidders shall submit the "DECLATION REGARDING THE MANDATORY PROCUREMENT OF SOLAR MODULES FROM CLASS I LOCAL SUPPLIERS" on the Letter Head of the Statuary Auditor/Cost Auditor of the company (In case of companies) or from a practicing cost accountant or practicing chartered accountant (In respect of suppliers other than companies) and same certified certificate shall be considered as bidder's compliance towards the DCR prior to the award. However, post the award supplier needs to submit the Form F-21 and Form F-22 and ensure the Domestic Content Requirement compliance.
35 | SPC | 3 of 10 | 6 (amending Clause 25 of the GPC) | Contract Performance Security/Bank Guarantee (CPBG) | Request to reduce it to 5% and balance 5% can be adjusted under BOS package. | Contractual | The terms and conditions of the tender document shall prevail.
36 | SPC | 7 of 10 | 10 (amending Clause 53 of GPC) | Latent defect liability | Significance of having 5 years of liability when we have a warranty in place? | Technical | The terms and conditions of the tender document shall prevail.
37 | GPC | 14 of 44 | 20.8 | The Supplier will not be entitled to claim any compensation for Force Majeure conditions and shall take appropriate steps to insure its men and materials utilized by it under the Contract. | Request SECI to modify the clause to state that if the Contract is terminated on account of Force Majeure Event, SECI will make payments of the modules that have been delivered as on the date of termination of the Contract. | Contractual | The terms and conditions of the tender document shall prevail.
38 | GPC | 9 of 44, 18 of 44, 19 of 44 and 24 of 44 | 6.5, 26.1.2(a), 26.2.3(d), 26.2.4(a), 34.3 | These clauses refer to the term 'Facilities' which has not been defined and indicate that the Supplier is obligated to attain completion of the Facilities within the prescribed timeline. It also requires the Supplier to remove debris, wreckage and rubbish from the site of the Owner post termination of the Contract, as is typically required in works contracts for development of solar power projects. Clause 34.3 also prohibits the Supplier to sell or remove any substances and materials obtained from excavation made for the purposes of the supply. | Considering that this is a supply contract, request SECI to remove references of Facility in the relevant clauses of the GPC and substitute it with the obligation of the Supplier to complete the supply of the Modules within the prescribed timeline. Further, we request SECI to remove Clause 34.3 as the supply obligations under the Contract will not involve excavation of the site in any manner. | Contractual | The terms and conditions of the tender document shall prevail.
39 | GPC/SPC | 30 of 44, 32 of 44, 7 of 10 | 50.1, 53.2.2, 55, 58, 12 (SPC) | Clause 50.1 requires the Supplier to rectify/replace any non-compliant materials or supplies provided by the Supplier on demand, irrespective of such supplies or materials being accepted by the Supplier. However, the provision does not specify a timeline to undertake such replacement/rectification. Clause 53.2.2 requires the Supplier to undertake such obligation within a period to be specified by the Project Manager in its demand. Clause 55 allows the Supplier to rectify any defects after takeover of the supplies within 1 month. Clause 58 requires the Supplier to rectify any defect or deficiencies in the supplies within 07 (Seven) days of his receiving the notice. Further, Clause 58, as amended by Clause 12 of the SPC, allows a period of 4 months of date of delivery of the modules at site to the Supplier to rectify defects in the Supplies. | Request SECI to please confirm the timeline within which the Supplier is obligated to rectify defects or deficiencies in the supply, prior to or after acceptance of the supplies by SECI in accordance with the Contract. | Contractual | If upon delivery, whether inspected and approved earlier or otherwise, the Solar PV Module is not in conformity with the specifications, the same shall be rejected by the Owner or his duly authorised representative and notification to this effect will be issued to the Supplier within 30 days from the date of receipt of the material at site. The supplier shall arrange for removal of the rejected item(s) within 15 days from the date of notification. In the event, the supplier fails to lift the materials within the said 15 days, the Owner shall be at liberty to dispose of such rejected item(s) in any manner as he may think fit and recover all the expenses from the Supplier. Further, the supplier shall arrange for replacement of defective modules for the period of 04 months from the date of delivery of such module pallets at site, in case such module pallets is not opened at the time of delivery and the visual inspection of such pallets is carried out at a later stage by the EPC Contractor.
40 | GPC/SPC | 42 of 44, 9 of 10 | 74 (GPC), 14 (SPC) | Clause 74 of the GPC already provides for a dispute resolution mechanism i.e., adhoc arbitration governed by the Arbitration and Conciliation Act, 1996 for disputes arising from the contract. However, Clause 14 of the SPC provides an alternative dispute resolution mechanism i.e., institutional arbitration administered by Indian International Arbitration Centre. | As Clause 14 of the SPC states “addition to the existing clause in the GPC” and does not replace the dispute resolution mechanism already given under Clause 74 of the GPC, it is unclear which dispute resolution mechanism will apply. Request SECI to clarify which dispute resolution mechanism will be applicable. | Contractual | Kindly refer to the order of precedence of different sections of the tender document. In case of any ambiguity, for the specific clause SPC will prevail over GPC.
41 | GPC | 44 of 44 | 74 | Clause 76 states that any hazardous material used during supply or used as part of the plant has to be taken back by the Supplier for recycling or dumping purpose after its operating life, so that it may not affect the environment or any living being. The Supplier shall fully comply with all environmental laws for the time being in force including Regulations issued by the State Pollution Control Board and the Notifications issued under the Environment (Protection) Act, 1986 from time to time, Hazardous Waste Management Rules in force from time to time. | Scope of supplier is to supply a single product - solar modules. This clause casts an additional scope of obligation on the Supplier to recycle the Modules for the life of the project (25 years)? Request SECI to therefore clarify whether the cost of removal of the modules from the site and the cost of recycling of the modules will be borne by the Supplier or SECI, so that Supplier will consider the cost of that obligations in its scope. | Contractual | The clause only talks about removal and recycle of hazardous material supplied at site by the supplier.
42 | SA-B | 2 of 7 | 1 | Adjustment of module evaluated bid value due to BoS cost. | The Module tender applies an 'adjustment due to BoS cost' to cover varying module efficiencies, which is also being applied to the BoS tender. There seems to be double counting of the BoS adjustment. | Contractual | Adjustment due to BoS cost refer to the price variation because of the variation in land, MMS, DC Cable, Excavation and Concrete cost arriving due to the different type of Module technology offered by various suppliers with the purpose to create a level playing field and maintain parity among various bidders offering different Module technology. And hence their is no as such double counting of the Adjustment factors.
43 | SECTION-I INVITATION FOR BIDS (IFB)/BID INFORMATION SHEET | 11 of 13 (14/241) | K | ONLINE BID-SUBMISSION DEADLINE - 20.05.2025 up to 1400 HRS | We request you to give us the extension of ONLINE BID-SUBMISSION DEADLINE for 3-weeks to 10-06-2025 up to 1400 HRS | Contractual | Please refer to ETS portal.
44 | SECTION-III BID DATA SHEETS (BDS) | 3 of 11 (70/241) | BID VALIDITY (ITB 14.1) | Bid Validity-The bid validity period shall be 180 (One Hundred and Eighty Days) from the date of opening of Techno-Commercial Bid (Envelope-I). | EMMVEE request to amend BID VALIDITY period to 90-days from date of opening of Techno-commercial bid (Enevelop-1) | Contractual | The terms and conditions of the tender document shall prevail.
45 | SECTION - V SPECIAL PURCHASE CONDITIONS (SPC) | 8 of 10 (137/241) | SPC No.-13/ Schedule of Rates & Payments (GPC clause 78) | Schedule of Rates & Payments Terms of 10%, 80% & 10% | SECI to Confirm the LC will be for 100 % of the Contract Value including GST. Emmvee Requests for 10% advance and balance 90% payment through irrevocable Letter of Credit for 30 days from the date of Tax Invoice with usance interest to account of SECI. EMMVEE request you to establish an irrevocable Letter of Credit (L/C) in favour of the supplier through the Employer's Bank for payments. | Contractual | The terms and conditions of the tender document shall prevail.
46 | SECTION-I INVITATION FOR BIDS (IFB)/BID INFORMATION SHEET | 11 of 13 (14/241) | I | CONTRACT PERFORMANCE SECURITY - 10% of the Total Project/Order Cost for a total period of 27 months. | We request you to amend CONTRACT PERFORMANCE SECURITY to 3% of the Total Project/Order Cost for a total period of 15 months. | Contractual | The terms and conditions of the tender document shall prevail.
47 | SPC | 7 of 10 - (136 / 241) | 10 - 53.2.13 Latent Defect Liability | Add following to the existing clause: 53.2.13 Latent Defect Liability: Notwithstanding, the defect liability period of 12 months above, the contract shall carry a latent defect liability of 5 years from date of delivery of material at site towards any defects in the modules supplied by the Supplier. | Please delete Latent Defect Liability clause, as latent Defect liability is NOT applicable as per prevailing industry norms. | Contractual | The terms and conditions of the tender document shall prevail.
48 | BID DATA SHEETS (BDS) | 3 of 11 - (70 /241) | 7 - Zero deviation & Rejection Criteria | Clause No. 18.1, Zero deviation & Clause No. 18.2, Rejection Criteria should be read in conjunction to each other & both clauses points mentioned should complement each other. | Unavoidable Deviations should be Allowed. | Contractual | The terms and conditions of the tender document shall prevail. However all such cases will be dealt on case to case basis.
49 | SoS & TS | 5 of 19 - (218 of 241) | PART – A: Scope of Supply - 1.1 | The scope of supply includes Manufacturing, Testing, Packing and Forwarding, Transportation to Site and Unloading of domestically manufactured Solar PV Modules with domestically manufactured solar cells | Kindly remove/delete the UNLOADING of modules from supplier scope. This should be in EPC or Owner Scope. | Technical | The terms and conditions of the tender document shall prevail.
50 | SoS & TS | 5 of 19 - (218 of 241) | PART – B: TECHNICAL SPECIFICATIONS - 2/2.1 Standards | IS 14286 (Part 1)-2019 - Terrestrial Photovoltaic (PV) Modules - Design Qualification and Type Approval, Part 1: Test Requirements (Second Revision) | IS 14286 (Part 1) – 2019-is equivalent IEC 61215-2016. Our modules are qualified with IEC 6125-2021 which is superior and latest version as compared to 2016. Also we comply to IS14286 -2010. As per the latest CRS scheme IS 14286:2023 is UNDER TESTING | Technical | Higher revision of standards specified are acceptable. Please refer Clause No. 2.1 of Technical Specifications
51 | SoS & TS | 5 of 19 - (218 of 241) | PART – B: TECHNICAL SPECIFICATIONS - 2 Standards | IS 14286: Part 1: Sec 1: 2019 - Terrestrial Photovoltaic (PV) Modules - Design Qualification and Type Approval, Part 1: Test Requirements, Section 1: Special requirements for testing of crystalline silicon photovoltaic (PV) modules (Second Revision) | IS 14286 (Part 1/Sec1) – 2019-is equivalent IEC 61215(Part 1/Sec 1)-2016. Our modules are qualified with IEC 6125-2021 which is superior and latest version as compared to 2016. Also we comply to IS14286 -2010. As per the latest CRS scheme IS 14286:2023 is UNDER TESTING | Technical | Higher revision of standards specified are acceptable. Please refer Clause No. 2.1 of Technical Specifications
52 | SOS &TS | 8 of 19 - (221 of 241) | PART B: TECHNICAL SPECIFICATIONS 5 Warranty - 5.1 Performance Warranty | 5.1 PV Modules shall be warranted for power output, as specified by the bidder in the Degradation Curve, for a minimum period of 25 years commencing from the date of the last Tax invoice raised under the contract. | Please clarify the same shall be applicable from the date of Tax Invoice | Technical | The terms and conditions of the tender document shall prevail.
53 | SOS &TS | 8&9 of 19 - (221/222 of 241) | PART B: TECHNICAL SPECIFICATIONS 5 Warranty - 5.3 Warranty Insurance | 5.3 - The Supplier under this Contract (i.e. the Insurer) shall purchase an Insurance Policy (i.e. Buyer's cover) to insure it's contractual liabilities arising out of the long-term performance and product warranties as per Clause above on PV Modules to be supplied to the buyer (i.e. Beneficiary - SECI) under the Contract. The aggregate limit of Insurer's liability under this Policy in respect of all Photovoltaic Modules covered under this Policy during the Policy Period shall be 6% of the Total Sum Insured, where Total Sum Insured shall be the total Invoice Value of capacity awarded under this Contract. This insurance should be valid for a period of 25 years from the date of last Tax Invoice under the contract and the claim period should extend for a minimum of 1 year beyond this date. Warranty Insurance certificate shall clearly identify the Beneficiary (i.e. SECI) along with project details viz. Location, Total Sum Insured and relevant contract reference details. | This insurance should be valid for a period of 25 years from the date of Tax Invoice, and the claim period should extend for a minimum of 1 year beyond this date is not acceptable/agree. Kindly remove this in tender. It is not practical for the claim period to extend for minimum of 1-year beyond this date, and it is therefore not acceptable. | Technical | The terms and conditions of the tender document shall prevail.
54 | SOS &TS | 9 of 19 - (222 of 241) | PART B: TECHNICAL SPECIFICATIONS 7 Manufacturing and Inspection | 7.3 For crystalline-Si modules Current binning of modules shall be employed so that current mismatch of modules in a pallet does not exceed 150 mA at Maximum Power (Imp). Different colour codes shall be provided on the modules as well as pallet for identification of different bins. The Supplier shall submit the binning scheme to the Employer for approval, prior to manufacturing | No colour code on the modules, only identification label I1/I2/I3 on the modules & boxes will be provided to identified the current class or Bins. Min of 3 bins with 150mA range of 1st bin and last bin shall be open, centre bin will be closed | Technical | Identification labels for bins in any form (including labels like I2/I3 etc.) shall be acceptable. Bin sizes shall be maximum 150 mA each. Please refer S. No. 5 of Amendment.
55 | SOS &TS | 8 of 19 - (221 / 241) | PART – C: PRE-DISPATCH INSPECTION PROTOCOL 5.1 BOM verification | 5.1 BOM verification - The details of materials used will be verified from the ERP/Manufacturing data and corroborated with the approved Bill of Materials. | Please note that verification from ERP is not industry practice, The details of materials used for the production shall be verified during the BOM verification at the shop floor. | Technical | It is clarified that the Supplier may corroborate the BoM used in manufacturing from manufacturing data maintained by the Supplier/manufacturer as per the Clause. Verification from ERP data is optional and not obligatory, as per the Clause.
56 | SOS &TS | 13 of 19 - (226 / 241) | PART – C: PRE-DISPATCH INSPECTION PROTOCOL 8 Inspection Process | 8.2 Visual Inspection-The inspector(s) shall visually verify characteristics of PV Module as per the Visual Inspection Criteria | As per the Emmvee Visual inspection criteria. | Technical | The terms and conditions of the tender document shall prevail.
57 | SOS &TS | 13 of 19 - (226 / 241) | PART – C: PRE-DISPATCH INSPECTION PROTOCOL 8 Inspection Process | 8.3 Electroluminescence (EL) Inspection- The inspector(s) shall visually verify characteristics of PV Module as per the Visual Inspection Criteria | As per the Emmvee EL inspection Criteria. | Technical | The terms and conditions of the tender document shall prevail.
58 | SOS &TS | 14 of 19 - (227 / 241) | PART – C: PRE-DISPATCH INSPECTION PROTOCOL 11 Disclaimer | Inspection by Owner or its authorized inspection agency does not absolve the responsibility of the Supplier to ensure quality during production of the material and its transport to site. Any damages during transport/ handling shall be replaced without any extra cost to the Owner. | If any damage during it transport/ handling shall be informed to the transporter or LR and with in concealment period mutually agreed by the both party | Technical | Please refer Clause 1.1 of SOS specifying the requirement of Supplier representative to be present at site during unloading and handing over of the consignment to the Employer representative/EPC Contractor. The identification of, and communication thereof to the Employer of any damaged modules to the satisfaction of both parties shall be ensured through the said arrangement.
59 | SECTION - V SPECIFIC ANNEXURE – B | 1 of 7 - (233 to 239) | PART – C: PRE-DISPATCH INSPECTION PROTOCOL 11 Disclaimer | BASIS FOR EVALUATION CRITERIA & SIMULATION PARAMETERS | We request that " Adjustment to Energy yield" should not be applicable as Energy yield depends on EPC work-cable sizing, inverter selection, grid outage and many other parameters in EPC scope. Moreover any simulation is subjective and speculative, and will not reflect the actual generation. We therefore request for deletion of this " Adjustment to Energy yield" in this Basis for Evaluation criteria. | Contractual | The terms and conditions of the tender document shall prevail.
60 | ITB | 15 of 51 - (31 to 241) | 15.10 Payment on Order Instrument (POI) against EMD: | As an alternative to submission of EMD, the supplier also has an option to submit a letter of undertaking issued by either of the following three organizations, viz. (i) Power Finance Corporation Limited or (ii) REC Limited. ….......... | Please include the "IREDA" as third organization here in this clause, which appears to be missed out here. | Contractual | The terms and conditions of the tender document shall prevail.
61 | ITB | 34 of 51 - (50 to 241) | B.2 Irregularities noticed after award of contract | (ii) After execution of contract and during Defect liability period (DLP)/ Warranty/ Guarantee Period: If an agency is found to have indulged in corrupt/ fraudulent/ collusive/ coercive practices, after execution of contract and during DLP/ Warranty/ Guarantee Period, the................. (iii) After expiry of Defect liability period (DLP)/ Warranty/ Guarantee Period If an agency is found to have indulged in corrupt/ fraudulent/ collusive/ coercive practices, after expiry of Defect liability period (DLP)/ Warranty/ Guarantee Period, the agency shall be banned for future business with Owner for a period specified in para B 2.2 below from the date of issue of banning order. | Please remove the word "Guarantee" in this clause | Contractual | The terms and conditions of the tender document shall prevail.
62 | GPC | 31 of 44 - (116 to 241) | 53.1 Guarantee/ Warranty | 53.1 Guarantee/ Warranty Supplier needs to ensure following Guarantees/ Warrantees to the best possible extent for the successful execution of the Contract. Subsequently, necessary Guarantee/ Warranty Certificate shall be produced by the Supplier. Guarantee/ Warranty as defined under Section VII, Scope of supply and technical specifications will prevail in this clause. | Please remove the word "Guarantee" in this clause | Contractual | The terms and conditions of the tender document shall prevail.
63 | Section I - Invitation for bids | 3 & 4 | 2.5 | The Bidder must offer following Module Technology: • Monocrystalline Si (Monoracial or Bifacial) • Thin Film CdTe | We request SECI to provide clarification on weight and dimensions of the solar panels to be supplied. | Technical | The Supplier may propose PV Modules meeting technical specifications provided in the tender document.
64 | Section III - Bid Data Sheet (BDS) Annexure and Qualifying requirements | 3 | 1.2 | Bidders participating under Route I needs to submit the ALMM listing proof in form of supporting documents. | We request SECI to change the timeline for the bidder to be included in ALMM to the date of Purchase Order as it will provide us with time to be included in the ALMM. | Contractual | The terms and conditions of the tender document shall prevail.
65 | Section V - Special Purchase Conditions | 2 | 3.0 (in the Table) | Under the above-mentioned total timelines of 12 months, PV Modules including Mandatory Spares under the award shall be supplied by the supplier in staggered deliveries during the delivery window of 8 months from (D+120 to D+360) days. For the calculation of Liquidated Damages for the delays, if any, the total timelines of 12 months will be calculated. | We request SECI to provide us with a specified time-line for supplying modules where the dates and quantity supplied are clearly defined | Contractual | The modules are to be supplied in the staggered delivery window of 08 months. However, the quantity wise exact delivery schedule will be finalized with the successful supplier in consultation with SECI post award.
66 | Section VIII - Schedule of Rates -1 | 2 | 10 | Mandatory spares required are in supplier's scope and deemed included in the quoted Lumpsum Prices. | We request SECI to keep Mandatory spares to be compensated in the bidding price itself. ' | Contractual | The terms and conditions of the tender document shall prevail.
67 | Section IV - General Purchase Conditions | 26 | 40.3 | The Supplier shall arrange for loading, transportation & unloading of materials at project site at his own cost & risk. | We request SECI to arrange the unloading facility at the site mentioned in the RfS | Contractual | The unloading of the PV Modules at site is in the scope of the BoS Contractor. The typographical error has been corrected, kindly refer to Amendment 01.
68 | Section IV - General Purchase Conditions | 18 | 26.1.1 | The Owner may at any time terminate the Contract for any reason by giving the Supplier a notice of termination that refers to this GPC Sub-Clause 26.1 | We request SECI to mandate the owner to give at least 1 month's notice before terminating the contract. | Contractual | The terms and conditions of the tender document shall prevail. However all such cases will be dealt on case to case basis with prior intimation.
69 | Section I - Invitation for bids | 4 | 3 | Domestic Content Requirement: 'The tender mandates use of both Solar Photovoltaic (SPV) Cells and Modules manufactured domestically as per specifications and testing requirements fixed by MNRE. For the supplies to be done under this tender, both the Solar Cells and Modules must be made in India and Modules shall be from the Manufacturers listed in ALMM list, published & updated by MNRE from time to time. In case of Crystalline Silicon Technology, all process steps and quality control measures involved in the manufacture of the Solar Cells and Modules starting from wafers until final assembly of the Solar Cells into modules shall be performed at the works of PV Manufacturers in India.' | We request SECI to allow the suppliers to import cells from another country because the cells having quality standards as M10, G12, and G12R per certifications are not found in India. To provide the Owner with best quality of Solar Modules, we request SECI to allow import of the cells only if they are certified with the credentials mentioned above. | Contractual | The terms and conditions of the tender document shall prevail.
70 | Section VII - Scope of Supply & Technical Specifications | 12 | 9(i) | The inspector(s) shall commence inspection process by randomly selecting samples from the list of module serial numbers (pallet-wise) provided by Supplier. Number of samples shall be chosen as per the inspection level mentioned in the table below and ISO 2859-1 (Single Sampling Plan for Normal Inspection). However, the inspector(s) shall reserve the right to switch to tightened or reduced level of Inspection as per the lot quality. Extracts of ISO 2859-1 relevant for determination of sample size are attached in Annexure-1. | We request SECI to kindly Clarify whether these inspections are Pre-Dispatch Only | Technical | Yes, the Inspections referred to in this Clause are with reference to pre-dispatch inspection of PV Modules manufactured under the Contract.
71 | IFB | 6 | 2.5 | Technology Offered: Thin Film/ Monocrystalline Si | Both technology modules should not be compared as same. | Technical | Terms and conditions of the tender shall prevail.
72 | IFB | 7 | 4 | PPP policy, Preference to make for local content make in India for more than 50% | Apart from DCR cell, if bidder use locally manufactured EVA,Glass and other BOM, how preference will be provided to those parties | Technical | No such specific incentive will be provided.
73 | GPC | 125 | 69, 69.5 | Module Insurance Warehouse to Warehouse | Warehouse will be in scope of which party ? Will required warehouse will comply insurance policy guidelines ? | Contractual | Query not clear. However, for the unloading at site, the storage facility will be arranged by the BoS Contractor.
74 | GPC | 126 | 71 | Comprehensive General Liability Insurance | Will the worker of third party shall be supplier responsibility ? | Contractual | Yes.
75 | SOS & TS | 216 | 1.1 | Unloading in Supplier Scope | After unloading when it will assumed as fully delivered ? | Contractual | The lot will considered fully delivered post the completion of visual inspection at site at the time of unloading. However, the supplier shall arrange for replacement of defective modules for the period of 04 months from the date of delivery of such module pallets at site, in case such module pallets is not opened at the time of delivery and the visual inspection of such pallets is carried out at a later stage by the EPC Contractor.
76 | GPC | 125 | 69.2, 69.3 | Supplier responsible till completion of supply. | Responsibility should end with in acceptance of lot at site. Once it is delivered then ownership shall changed from supplier to buyer and during any unforeseen event for purpose of FIR owner of material can lodge FIR. | Contractual | The lot will considered fully delivered post the completion of visual inspection at site at the time of unloading. However, the supplier shall arrange for replacement of defective modules for the period of 04 months from the date of delivery of such module pallets at site, in case such module pallets is not opened at the time of delivery and the visual inspection of such pallets is carried out at a later stage by the EPC Contractor. And hence the ownership will be decided in the same fashion as per the acceptance of material.
77 | GPC | 125 | 69.4 | Supplier responsible till completion of project | Supplier responsibility should end after successful delivery, post delivery this responsibility should lie with installer or EPC player as insurance cant be for indefinite period. | Contractual | The lot will considered fully delivered post the completion of visual inspection at site at the time of unloading. However, the supplier shall arrange for replacement of defective modules for the period of 04 months from the date of delivery of such module pallets at site, in case such module pallets is not opened at the time of delivery and the visual inspection of such pallets is carried out at a later stage by the EPC Contractor. And hence the ownership will be decided in the same fashion as per the acceptance of material.
78 | GPC | 125 | 69.7 | Transit insurance and workmen compensation | This workmen compensation should be related to supplier part not of third party | Contractual | Query not clear.
79 | GPC | 126 | 70 | Transit/ Cargo Insurance | Since Its Warehouse to warehouse, will SECI provide proper warehouse with requisite facilities as per insurance facility. Aside after delivery since ownership will transfer to SECI and then to integrator, in this case how insurance will work. | Contractual | For unloading at site, the storage facility will be arranged by the BoS Contractor.
80 | GPC | 127 | 71 | Comprehensive General Liability Insurance | Sub-supplier should be from supplier only not the hired one from buyer for other plant related activities | Contractual | Yes.
81 | SA-B | 234 |  | Basis of Evaluation criteria | Request to enlighten the factors taken into consideration of the technology selection for the bid evaluation. (Adjustment to quoted bid) Can adjustment to quoted bid factor negative | Contractual | To maintain the parity during the Evaluation between bidders supplying Modules with different specifications and efficiency, the Adjustment factor due to the change in Balance of Systems cost and the Adjustment factor due to change in Energy Yield has been considered in the Quoted Bid Value of the bidder. The Adjustment due to Balance of System caters to cost change related to Land Area requirement, MMS, Excavation, Concrete and DC Cable. The Adjustment due to Energy Yield caters to change in total energy yield over the total period of the project. The adjustment factor can be positive and negative depending on the type of Module Technology and Module Specifications the bidders offers and same will be adjusted in the Quoted Bid Value of the bidder to bring all the bidder on same level playing filed for the purpose of Evaluation and Auction.
82 | SOS & TS | SoS & TS Page 9 of 19 | 7.3 | For crystalline-Si Modules, current binning of modules shall be employed so that current mismatch of modules in a pallet does not exceed 150 mA at Maximum Power (Imp). Different colour codes shall be provided on the modules as well as pallet for identification of different bins. The Supplier shall submit the binning scheme to the Employer for approval, prior to manufacturing. | We have 2 Current bin I1 & I2. I1 is closed bin & I2 is open. No need of identification of different bin pallets as we have current bin printed on module back label as well as in front of every modules listed in the packing slip of pallets. | Technical | Identification labels for bins in any form (including labels like I2/I3 etc.) shall be acceptable. Bin sizes shall be 150 mA each. Please refer S. No. 5 of Amendment.
83 | SOS & TS | SoS & TS Page 7 of 19 | 4.5 | For c-Si modules, the module frame shall be made of anodized Aluminium. It shall have provision for earthing to connect it to the earthing grid. The anodization thickness shall be 15 micron (12 micron in case of 6005 Grade Aluminium). | Request to change the wording from '15 micron' to '≥15 micron' or 'minimum 15 micron' and '12 micron' to '≥12 micron' or 'minimum 12 micron' | Technical | The specifications provided are the minimum requirement. Bidder may propose greater anodization thickness. Please refer S. No. 1 of Amendment 1.
84 | SECTION - VII | SoS & TS Page 6 of 19 | 4.1.1 | PART – B: TECHNICAL SPECIFICATIONS Glass/Glass Modules: Glass shall have minimum 2 mm thickness on each side. | Glass used will be 2mm thickness with a manufacturing tolerance of -/+ 0.2mm | Technical | Manufacturing tolerance of */- 0.2 mm is acceptable.
85 | SECTION - VII | SoS & TS Page 5 of 19 | 2.1 | IS/IEC 61701: 2011 - Salt Mist Corrosion Testing of Photovoltaic (PV) Modules – Severity 1 | IS/IEC 61701: 2011 - Salt Mist Corrosion Testing of Photovoltaic (PV) Modules – Severity 6 can be accepted | Technical | Yes.
86 | SECTION - VII | SoS & TS Page 14 of 19 | 9 | Re-inspection and review | In case of lot rejection resampling will be done with same sampling plan and AQL. If fail reject lot | Technical | Terms and conditions for re-inspection and review (Clause No. 9) of the tender shall prevail. Acceptance / Rejection of lot shall be based on Clause No. 7 of PRE-DISPATCH INSPECTION PROTOCOL.
87 | SECTION - VII | SoS & TS Page 3 of 19 | 1.5 | The Supplier shall submit PAN file of the PV Modules to be supplied (certified by an ILAC member signatory accredited laboratory) at the time of Bidding. | The supplier shall provide PAN file before LOI | Contractual | As PAN File submission is mandatory for calculating the Adjustments factors during the Evaluation phase and hence, the terms and conditions of the tender document shall prevail.
88 | SoS & TS | 222 | 7.3 | For crystalline-Si Modules, current binning of modules shall be employed so that current mismatch of modules in a pallet does not exceed 150 mA at Maximum Power (Imp). Different colour codes shall be provided on the modules as well as pallet for identification of different bins. The Supplier shall submit the binning scheme to the Employer for approval, prior to manufacturing | Request SECI to kindly consider Wattage binning without colour coding which is widely used in market it will also reduce the number of Bins compared current binning | Technical | Terms and conditions of the tender shall prevail. In addition, please refer S. No. 5 of Amendment 1.
89 | SoS & TS | 222 | 7.3 | For crystalline-Si Modules, current binning of modules shall be employed so that current mismatch of modules in a pallet does not exceed 150 mA at Maximum Power (Imp). Different colour codes shall be provided on the modules as well as pallet for identification of different bins. The Supplier shall submit the binning scheme to the Employer for approval, prior to manufacturing | Requesting SECI to kindly increase the current binning range from 150 mA to 200 mA which will help reduce the no. of bin and help to improve the Manufacturing/Production efficiency | Technical | Terms and conditions of the tender shall prevail. In addition, please refer S. No. 5 of Amendment 1.
90 | SoS & TS | 227 | 8.4 | Electrical Characteristics | As separate Insulation test & Continuity test of equipotential bonding (for framed modules only) is unavailable but this all three tests are covered in the Hi-Pot Test itself which is as per the industry standard. Request SECI to consider the Hipot test as the same. | Technical | The terms and conditions of the tender document shall prevail.
91 | BDS Page 3 of 11 | 70/241 | 6 | The bid validity period shall be 180 (One Hundred and Eighty Days) from the date of opening of Techno-Commercial Bid (Envelope-I). | Considering the volatility of the market we request SECI to kindly make the bid validity period to 60 Days. | Contractual | The terms and conditions of the tender document shall prevail.
92 | NA | NA | NA | General Query | Request SECI to kindly clarify if we can supply 78 full cell (156 Half cut cell) modules to achieve higher power class module ≥ 540 Wp. | Technical | Yes, the bidder may supply higher Wattage than 540 Wp subject to the compliance of Technical specifications provided in the tender.
93 |  | 235 | 1 | η_quoted : PV Module (%) Efficiency quoted by the Bidder | The total capacity of the tender 260 MWp will be having the multiple power bins i.e. 580Wp, 585Wp, 590Wp etc with variable efficiency. Tender says supplier has to quote a single efficiency value against the "η_quoted" parameter. Requesting SECI to clarify that "η_quoted" efficiency in the formula is the weighted avg. for the all power bins supplied for the complete 260 MWp capacity. | Technical | Bidder has to quote single efficiency for Bid- Evaluation purpose. However, please note that, the Module Efficiency provided herein shall be the minimum value and may be increased without altering the Module Dimensions at the time of supply. The PV Module dimensions - Length and Width of the PV Modules shall not be changed at the time of Supply from the values specified in FORM T-01.
94 | GPC Page 26 of 44 | 111/241 | 40.3 | The Supplier shall arrange for loading, transportation & unloading of materials at project site at his own cost & risk | We request SECI to kindly include the scope of unloading of PV modules at site to the EPC contractor. The EPC contractor will already have the required unloading equipment and resources available at site, making them better positioned to handle the activity. If unloading remains in the supplier's scope, the supplier will be required to deploy special manpower and equipment exclusively for this purpose. Post material reached the site the transit insurance will only be valid for 24 Hrs, this puts the supplier at the risk which leads to increase in the cost. Hence putting the unloading in the EPC scope will help SECI to reduce the price. | Contractual | The unloading of the PV Modules at site is in the scope of the BoS Contractor. And the typographical error has been corrected, kindly refer to Amendment 01.
95 | GPC Page 26 of 44 | 111/241 | 40.3 | The Supplier shall arrange for loading, transportation & unloading of materials at project site at his own cost & risk | Kindly define the PV Module handover SOP at site to enable the unloading and acceptance of the material within the 24 Hrs for the receipt at site. Acceptance of material shall be provided on Lorry Receipt (LR) copy with the sign and stamp of the SECI representative. | Contractual | The detailed SOP will be shared with the successful supplier post award in consultation with the Project Manager deployed at site by SECI.
96 | SPC Page 8 of 10 | 137 | 13 | I) Interest free advance (optional) of 10% of the total value of Supply portion shall be released to supplier upon receipt of unconditional acceptance of PO, detailed Performa invoice of contractor and against submission of unconditional & irrevocable Advance Bank Guarantee (ABG) with a validity period up to date of final supply amounting to 100% of total advance amount. The ABG needs to be submitted in addition to the Contract Performance Security. | Request SECI to kindly revise the Interest free advance from Ten percent (10%) to Fifteen percent (15%) upon receipt of unconditional acceptance of PO, detailed Performa invoice of contractor and against submission of unconditional & irrevocable Advance Bank Guarantee (ABG) with a validity period up to date of final supply amounting to 100% of total advance amount. | Contractual | The terms and conditions of the tender document shall prevail.
97 | SPC Page 8 of 10 | 137 | 13 | (iii) Ten percent (10%) payments of the total value of Supply portion shall be paid on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents (except Advance Bank Guarantee) indicated under clause I) above, Contractor’s detailed invoice & packing list identifying contents of each shipment, evidence of dispatch (GR/ LR copy), Manufacturer’s/ Contractor’s Guarantee certificate of Quality and MDCC (Material Dispatch Clearance Certificate) issued by Owner’s authorized representative in original and Material Receipt Note (MRN). | Request SECI to kindly revise the Ten percent (10%) payments to Five percent (5%) on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents. | Contractual | The terms and conditions of the tender document shall prevail.
98 | SPC Page 2 of 10 | 131 | 3 | S. No. Stage Reference from D 3.1 Issue of Purchase Order or Notice to Proceed (NTP): Zero Date (D) 3.2 Submission of Drawing and Test Certificates: D + 60 days 3.3 Manufacturing Clearance: D + 120 days 3.4 Supplies at site: D + 120 to D + 360 days | As per our earlier experience in the market even when the deliveries were allowed for the larger time span we were asked to supply the modules in specific and limited time as per the EPC requirement, which interrupted the Module Production planning. Hence supplier should be free to supply the Modules anytime within the given time schedule and intimate the SECI as per the tender requirement. If there is special requirement to supply Modules in a specific time within the schedule, it should be communicated to supplier at least 4 months prior, which will enable supplier to plan the production accordingly. | Contractual | The staggered supply window of the Modules will be decided in mutual consultation with SECI, Module Supplier and the BoS Contractor at the time of Manufacturing Clearance.
99 | SA-B Page 6 of 7 | 238 | P | Spectral correction: Applicable only for Thin-film CdTe | Per tender Spectral correction gain is allowed for Thin Film technology whereas Bifacial gain is not allowed for Crystalline technology in the Energy Yield adjustment factor. Request SECI to disallow spectral correction gain as it is a very subjective opinion. The spectral correction gain for the project location is coming to ~1.8% which unduly favours thin film technology which is not as mature and widely accepted technology as crystalline technology. Of the global PV installations, more than 90% is crystalline technology. As per our understanding there are no Central or State statutory authorities which have verified and established the spectral correction gain as a legitimate performance parameter of thin film technology (Cd-The). There are also no independent Standards to measure and verify the same claim as well. Further, widely used energy simulation software - PVSYST clearly discounts the spectral correction gain as a disclaimer in the simulation. Pls find attached the screenshot of the same. Basis above, It is our firm opinion that Spectral correction gain is not a widely accepted performance parameter and is not verified and established as a clear gain by any of our Statutory authorities/bodies or internationally accepted standards. Hence, allowing spectral correction gain for thin film technology provides undue advantage to thin film technology (Cd-Te) and puts crystalline technology which is a more mature and widely accepted technology at a disadvantage. We request you to kindly reconsider and remove spectral correction gain for thin film technology in Energy Yield Adjustment factor calculations. | Technical | Bifacial gain is allowed for Bifacial Modules in the Energy Yield adjustment factor. Please refer to Sl. No. 11, Sl. No. 12 and Sl. No. 20 of Amendment 1
100 | SA-B Page 4 of 7 | 236 | NA | Bifacial gain | Crystalline PV Technology is the most mature and widely accepted technologies in PV industry. More than 90% of installations globally are Crystalline technology which is testament to its proven performance and reliability in the market. The tender is calling for supply of modules from both crystalline and thin film (Cd-Te) technologies. In crystalline technology, Bifacial modules are accepted per tender. Bifacial modules are widely popular and considered in PV installation due to the additional generation from rear side of the module. This additional generation gain is usually termed as bifacial gain. In the energy yield adjustment factor calculations bifacial gain is not considered presently. Widely used energy simulation software - PVSYST clearly itemises and provides the bifacial gain for applicable bifacial modules. Request SECI to consider and allow bi-facial gain in the energy yield adjustment factor calculations for bifacial modules. | bin | Simulation parameters for Bifacial Systems have been added. Please refer to Sl. No. 11, Sl. No. 12 & Sl. No. 20 of Amendment 1
101 | SA-B | Page 6 of 7 | J | SPsim_P75 P75 Specific production obtained from PVsyst simulation (kWh/kWp) Note: In case of thin film modules, first year degradation shall be deducted from Simulated Specific production to arrive at final SPsim_P75 value. | Request SECI to provide the value of the first year degradation value for the thin film Technology. The LID loss claimed for Thin Film technology PV module available under ALMM list is zero. However, it is pertinent to note that the warranty start point is mentioned as 98% in the datasheet for corresponding modules in thin film technology (Cd-te0. If the first year degradation is not considered in the calculations for energy yield adjustment factor, then the simulated energy yield for all 25 years will be higher and not realistic which will bestow an undue advantage to the thin film technology (Cd-Te). Request SECI to clarify and confirm that the first year degradation value will necessarily be deducted from the SPsim-P75 value. | Technical | First year degradation shall be provided by the manufactured in FORM-T-01 & T-02. the Values provided in the above form shall be considered for warranty purpose. In addition, please refer S. No. 9 of Amendment 1.
102 | GPC Page 26 of 44 | 111/241 | 41.1 | Supply in Monsoon and Dewatering: Unless otherwise specified elsewhere in the tender, the execution of the Supply may entail supplying in the monsoon also. The Supplier must maintain a minimum work force as may be required for the job and plan and execute the supply according to the prescribed schedule. No extra rate will be considered for such supply in monsoon. | SECI shall ensure a motorable access road for movement of 40 feet container vehicle movement till the module unloading point at site, even during the monsoon season. If there is any disruption to access of road near site, we request SECI to arrange alternative unloading locations and roads so that unloading of materials can be made immediately after delivering at site to avoid demurrage charges from transporter. Any double handling will be in the SECI scope. | Contractual | The approach road and unloading at site will be decided in mutual consultation with SECI, Module Supplier and the BoS Contractor. And hence the concern mentioned will be taken care beforehand.
103 | SPC Page 7 of 10 | 136 | 10 | Latent Defect Liability: Notwithstanding, the defect liability period of 12 months above, the contract shall carry a latent defect liability of 5 years from date of delivery of material at site towards any defects in the modules supplied by the Supplier | We are already providing a 10-year product warranty and a 25-year power output warranty for the modules. In view of this, a 5-year latent defect liability results in overlapping coverage. Therefore, we request that the latent defect liability be limited to 1 year from the date of delivery at site, in line with the standard defect liability period. | Contractual | The terms and conditions of the tender document shall prevail.
104 | IFB Page 4 of 13 | 7 | 2.6 | Location of the project site – Badnawar, Dhar, Madhya Pradesh. | Requesting the SECI to share the detailed delivery address with the pin code for accurate transport distance and planning. | Technical | Kindly refer to Technical Specification section of the tender document. The project site is divided into three locations – Gadhi (Badnawar Tehsil), Rajod & Nawapada (Sardarpur Tehsil)
105 |  |  |  | General Specification of module | Request SECI to kindly clarify is there any restriction on Min and Max Wattage and the dimension of the module. Please confirm if this dimension is acceptable 2456 x 1134 x 30/35 | Technical | There is no restriction on the minimum or maximum wattage or dimensions of the module; however, it must meet the minimum efficiency requirement and comply with all other criteria outlined in the Technical Specifications.
106 | SPC Page 8 of 10 | 137 | 13 | Eighty percent (80%) of the total value of Supply portion shall be paid upon dispatch of Solar PV Modules (along with mandatory spares) from manufacturer's works on pro-rata basis on production of invoices and satisfactory evidence of shipment which shall be original Goods Receipt or receipted GR/Rail Receipt including Material Dispatch Clearance Certificate (MDCC) issued by the Owner’s Corporate QA & I representative and copy of Insurance for the supplied goods issued by the Supplier. | We request SECI to kindly accept copies of the required dispatch documents — including Goods Receipt (GR), receipted GR/Rail Receipt, Lorry Receipt (LR), Material Dispatch Clearance Certificate (MDCC) issued by the Owner’s Corporate QA & I representative, and Insurance copy — for the purpose of raising the supply payment claim. The original documents are held by the transporter during the transit period, which may cause delays in submission. Acceptance of copies will allow us to submit the claim immediately after dispatch, enabling timely payment processing. | Contractual | The terms and conditions of the tender document shall prevail.
107 | SPC Page 8 of 10 | 137 | 13 | (iii) Ten percent (10%) payments of the total value of Supply portion shall be paid on Pro rata basis against supply, receipt and acceptance of Materials at site on submission of documents (except Advance Bank Guarantee) indicated under clause I) above, Contractor’s detailed invoice & packing list identifying contents of each shipment, evidence of dispatch (GR/ LR copy), Manufacturer’s/ Contractor’s Guarantee certificate of Quality and MDCC (Material Dispatch Clearance Certificate) issued by Owner’s authorized representative in original and Material Receipt Note (MRN). | We request SECI to kindly provide the detailed SOP for issuing the MRN in order to claim the payment on time. We have experienced that the delayed issuance of MRN from the Owner resulted in late payments to the supplier. We request that the Material Receipt Note (MRN) be issued within one week of the material receipt at the site. This will ensure that all payment claims can be processed in a timely manner. If MRN is not received in a weeks time then deemed MRC shall be allowed to claim the pending payment. The delay in issuing the MRN could affect the overall payment timeline, and setting this one-week limit will help avoid any delays and ensure that payments are processed within the agreed timeframe. | Contractual | The detailed SOP regarding the issuance of MRN will be share by the Project Manager of SECI to the Successful supplier.
108 | General |  |  |  | Requesting SECI to kindly share the calculation/Basis behind the constants used in the Bid evaluation formula for the better understanding and clarity of the bid evaluation methodology | Contractual | The basis of the calculation of Formula will not be shared with the bidders, being the internal confidential document approved by SECI's Management.
109 | IFB Page 11 of 13 | 14 | K | ONLINE BID-SUBMISSION DEADLINE 20.05.2025 up to 1400 HRS | Request you to kindly extend the bid submission date by at least 3 weeks, it will enable us to do the detailed evaluation of the some new aspects of the tender document like new bid evaluation criteria and offer you the best possible solution. | Contractual | Please refer to ETS portal.
110 | SoS & TS Page 3 of 19 | 216 | 1.5 | 1.5 The Supplier shall submit PAN file of the PV Modules to be supplied (certified by an ILAC member signatory accredited laboratory) at the time of Bidding. | Request SECI to remove the requirement the PAN file submission requirement, it can be submitted during the supply of the modules. This will enable the bidder to include the future products also. At the bidding stage request you to accept the OEM approved PAN file (without Third Party approval). | Technical | The terms and conditions of the tender document shall prevail.
111 | SA-B Page 3 of 7 | 235 | 2 | 2. Adjustment due to Energy Yield (C): | As multiple technology Modules are qualified to bid for this tender and Bid evaluation criteria is comprised of adjustment due to energy yield which is a function of yearly linear degradation value, Successful bidder will get an advantage due to this parameter. Request SECI to kindly put a penalty clause linked to the generation for the non adherence to the quoted degradation. This will help the SECI to protect their generation for 25 years and prevent any misuse of the evaluation criteria. | Technical | Bidder must diligently quote the degradation value and must abide by the same during the entire period of Module. If any bidder for the purpose of winning the order found to quote the degradation value which the bidder will not abide during the execution stage, then such matter will be taken serious and suitable resolution will be carried out by SECI in line with the terms and conditions of the tender document.
112 | SoS & TS Page 12 of 19 | 225 | 6 | 6 Sampling Process | We are following the below standard practice for all CPSU (NTPC, SJVN, NHPC, NLC, etc) and request you to approve the same. | Technical | Please refer S. No. 6 of Amendment 1.

## Amendment 1
Sl No. | Tender Section | Page No. | Clause No | Description as per Tender Document | Amendment
1 | SoS & TS | 7 of 19 | 4.5 | The anodization thickness shall be 15 micron (12 micron in case of 6005 Grade Aluminium). | The anodization thickness shall be >=15 micron (>=12 micron in case of 6005 Grade Aluminium).
2 | SoS & TS | 7 of 19 | 4.7 | Each PV Module shall be provided with a RFID tag (This can be inside or outside the laminate, but must be able to withstand harsh environmental conditions). | Each PV Module shall be provided with a RFID tag (This can be inside or outside the laminate, but must be able to withstand harsh environmental conditions). The Supplier shall also provide 5 No. RFID tag readers along with the Supply.
3 | SoS & TS | 8 of 19 | 4.6 | Junction box with "4 sq.mm. copper cable of 1200 mm shall be provided." | Junction box with 4 sq.mm. copper cable of 1200 mm shall be provided. In the case of thin film module, the cable shall be 2.5 sq.mm.
4 | SoS & TS | 5 of 19 | 2.1 | IS 17210:Part 1:2019 / IEC TS 62804-1:2015 for PID test. | IS 17210:Part 1:2019 / IEC TS 62804-1:2015 for PID test for Cr-Si Modules and IEC TS 62804-2:2022 for Thin Film Modules.
5 | SOS &TS | 9 of 19 - (222 of 241) | PART B: TECHNICAL SPECIFICATIONS 7 Manufacturing and Inspection | 7.3 For crystalline-Si modules Current binning of modules shall be employed so that current mismatch of modules in a pallet does not exceed 150 mA at Maximum Power (Imp). Different colour codes shall be provided on the modules as well as pallet for identification of different bins. The Supplier shall submit the binning scheme to the Employer for approval, prior to manufacturing | 7.3 For crystalline-Si modules Current binning of modules shall be employed so that Maximum Power current (Imp) mismatch of modules in a bin does not exceed 150 mA. A bin identification methodology shall be employed by the manufacturer (eg. different colour codes/Identification labels like I2/I3 etc.) on the modules as well as pallet for identification of different bins. The Supplier shall submit the binning scheme to the Employer for approval, prior to manufacturing
6 | SoS & TS Page 12 of 19 | 225 | 6 | 6 Sampling Process | Electroluminescence: Special inspection Level - S-2
7 | SoS & TS | 3 of 19 | 1.5 | The Supplier shall submit PAN file of the PV Modules to be supplied (certified by an ILAC member signatory accredited laboratory) at the time of Bidding. | The Supplier shall submit PAN file of the PV Modules to be supplied (certified by an ILAC member signatory accredited laboratory) at the time of Bidding. Test reports used for PAN file creation shall also be submitted along with the bid. In case user defined IAM profile is used in PAN file (applicable to both Cr-Si and Thin Film Modules) or spectral correction gain is claimed (applicable to Thin Film Modules), test report as per IEC 61853-2 shall be submitted.
8 | SA-B | 4 of 7 | 3 | Note: In case of thin film modules, first year degradation shall be deducted from Simulated Specific production to arrive at final SPsim_P75 value. | VOID
9 | SA-B | 6 of 7 | 4 (5-H) | Module efficiency loss: 0.0 % | Module efficiency loss: 0.0 % - For Crystalline modules Module efficiency loss: First Year Degradation - For Thin Film modules
10 | SA-B | New Clause | 4 | - | 2. Project Settings (v) Albedo - 0.16
11 | SA-B | 7 of 7 | 4 | - | 6. Bifacial System (applicable only for Bifacial Module) i. Use Unlimited sheds 2D-model ii. Ground Albedo- iii. Shade transparent fraction - 0% iv. Structure Shading factor - 5% v. Mismatch loss factor - 10% vi. Height above the ground- 0.5m vii. Bifaciality factor - As per module manufacturer specifications
12 | Form T-01 | New | 25 | - | 25. Bifaciality factor (tested as per IEC 60904-1-2; applicable only for Bifacial Module)
13 | SA-B | 5 of 7 | 4
14 | IFB | 3 of 13 | 2.3 | Illustration for single package: Quoted Package Capacity = 260 MWp Minimum Awarded Package Capacity = 0.90 × 100 = 234 MWp Maximum Awarded Package Capacity = 1.10 × 100 = 286 MWp | Illustration for single package: Quoted Package Capacity = 260 MWp Minimum Awarded Package Capacity = 0.90 × 260 = 234 MWp Maximum Awarded Package Capacity = 1.10 × 260 = 286 MWp
15 | ITB | 10 of 51 | 10 | II. Online Documents/Soft Copy | Add following to the existing clauses: Third party verified PAN file along with test reports used for PAN file creation must be submitted under Online Documents.
16 | SOS & TS | 3 of 13 | 1.1 | The scope of supply includes Manufacturing, Testing, Packing and Forwarding, Transportation to Site and Unloading of domestically manufactured Solar PV Modules with domestically manufactured solar cells. Unloading of the consignment (i.e. PV Modules supplied under this Contract) shall be the responsibility of the Employer. | The scope of supply includes Manufacturing, Testing, Packing and Forwarding & Transportation to Site of domestically manufactured Solar PV Modules with domestically manufactured solar cells. Unloading of the consignment (i.e. PV Modules supplied under this Contract) shall be the responsibility of the BoS Contractor.
17 | IFB | - | - | Add following to the existing clause | ALMM (Approved List of Models and Manufacturers) for solar cells With reference to the MNRE Order No. 283/59/2024-GRID SOLAR, all the bidder must the follow the ALMM list for Solar Cells. The detailed order is attached as Annexure 1 to the Amendment.
18 | Section VIII Schedule Of Rate | - | - | Add following to the existing clause | The bidders must mandatorily quote the GST for Modules Supply and Module Freight part in line with the current prevailing GST rate as per the applicable HSN Code. The current prevailing rates for the Domestic Modules supply is 12% & its 18% on the services part. The bidders are required to exercise utmost diligence in mentioning such GST % , else SECI reserves all rights to correct the taxation part so as to arrive at the right taxation percentage & thereby the final total cost (If corrected)
19 | SOS & TS | 5 of 19 | 1.2 | The PV Module shall be enlisted in ALMM – List I in accordance with extant provisions of Approved Models and Manufacturers of Solar Photovoltaic Modules (Requirements for Compulsory Registration, Order, 2019) and subsequent amendments. | The PV Module shall be enlisted in ALMM – List I in accordance with extant provisions of Approved Models and Manufacturers of Solar Photovoltaic Modules (Requirements for Compulsory Registration, Order, 2019) and subsequent amendments and these Solar PV modules shall be manufactured using solar cells from ALMM List-II.
20 | SOS & TS | 5 of 19 | 2.1 | -
21 | SOS & TS | 14 of 19 | 8.4 | 8.4 Electrical Characteristics: The following tests shall be performed on min 10 nos. of PV Modules selected from the Sample from the lot. | 8.4 Electrical Characteristics: The following tests shall be performed on PV Modules.